## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ORGRAM Piped Water Supply Scheme & Sibda Colony habitation, Bhatar Block under Burdwan Division, PHE Dte.(Agreement No. 59/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000123/2020-2021 | 4886/BWD | 07/12/2020 | 07/03/2021 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 97.01 | 28.41 | 29.28 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for Orgram (Zone-I) & it's adjoining mouzas W/S. scheme under Burdwan Division, P.H.E. Dte.Ref. Drawing No.PC-I/OHR/7/2012 Dated 07.06.2012. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000448/2021-2022 | 764/BWD | 07/02/2022 | 06/08/2022 | S.N. ENTERPRISE | 67.98 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Shifting and relaying of Distribution system and Rising main at OHR site of Orgram Piped W/S Scheme (Zone-II) at Bhatar Block under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000566/2023-2024 | 655/DSD | 24/08/2023 | 23/09/2023 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ORGRAM Piped Water Supply Scheme at Salkuni, Orgram (10 Nos Habitation), & Silakote Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte._2ND CALL.(Agreement no. 102/SE/CC/PHE/Dte of 2020-2021) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000424/2020-2021 | 1086/BWD | 08/02/2021 | 09/05/2021 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 81.92 | 44.04 | 53.76 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Extension of distribution main for providing FHTC at Shikarpur village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000290/2021-2022 | 719/DSD | 17/12/2021 | 16/01/2022 | DHIRENDRANATH SOM | 3.28 | 3.28 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Extension of distribution main for providing FHTC at Shilakot village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte.[Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000289/2021-2022 | 718/DSD | 17/12/2021 | 16/01/2022 | DHIRENDRANATH SOM | 3.15 | 3.1 | 98.48 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Extension of distribution main for providing FHTC at Shalkuni village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000288/2021-2022 | 717/DSD | 17/12/2021 | 16/01/2022 | DHIRENDRANATH SOM | 3.62 | 3.62 | 100 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Extension of pipeline at Bagmara village of Orgram (Z-II) and its adjoining mouzas piped water supply scheme at Bhatar Block within Burdwan Sadar Sub-Division, under Burdwan Division, PHE Dte.[Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000781/2021-2022 | 952/BSD | 23/07/2021 | 22/08/2021 | M/S S. CHOUDHURY | 2.01 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Vehicle bill (Car No.-WB-41H-3668) for the month of July to September'2023. |  |  | BILL/01679/2023-2024 | 1142/JJM | 29/12/2023 | 29/12/2023 | MD HASIN | 0.86 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Restoration of damaged flanks due to laying of HDPE pipe line along the flank of Burdwan Katwa Road from 14.70 kmp to 16.20 kmp in the district of Purba Bardhaman under Bardhaman Division,P.W.D. |  |  | BILL/00711/2024-2025 | 867/JJM | 23/09/2024 | 23/09/2024 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 7.9 | 0 | 0 | 0
Total | [13 empty] | 268.47 | 82.44 | 30.71