## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Extension of UPVC distribution pipeline in connection with FHTC for Masagram (Zone-I) & adjoining mouzas water supply scheme at Jamalpur Development Block under Burdwan Division, PHE Dte.[Gr.-B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000419/2021-2022 | 1112/BSD | 23/08/2021 | 07/10/2021 | M/S ASHA CONSTRUCTION | 4.71 | 4.71 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Masagram Piped Water Supply Scheme at Habaspur Village, Chouberia Village, Ballabhbati Village & Masagram (4 Nos. habitations), Jamalpur Block under Burdwan Division, PHE Dte. (Agr. No. 710/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000342/2020-2021 | 1578/BWD | 22/02/2021 | 23/04/2021 | MD HASIN | 60.21 | 65.84 | 109.36 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Masagram Piped Water Supply Scheme at Dadpur Village, Sarangpur Village (2Nos. habitations) & Sanchra Village, Jamalpur Block under Burdwan Division, PHE Dte.(Agreement No. 753/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000437/2020-2021 | 1599/BWD | 22/02/2021 | 23/04/2021 | M/S ASHA CONSTRUCTION | 65 | 98.84 | 152.07 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Construction of Boundary Wall at 2nd T/W Site of Masagram Zone-I Water Supply Scheme under Jamalpur Block of Burdwan Division, PHE Dte (Length-50.0 Mtr,Col-17 Nos). Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000443/2021-2022 | 201/BSD | 01/02/2022 | 18/03/2022 | SANDIPAN SENGUPTA | 3.12 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Extension of UPVC distribution pipeline in connection with FHTC for Masagram (Zone-II) and its adjoining mouzas water supply scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. (Habaspur Habitation) [Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000535/2021-2022 | 1206/BSD | 09/09/2021 | 09/10/2021 | MD HASIN | 4.85 | 4.84 | 99.77 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Laying of 200mm.dia. HDPE Distribution pipe line (Node No.118 to 119) for Masagram (Zone-I) & adjoining mouzas Water Supply Scheme at Jamalpur Development block under Burdwan Division,PHE Dte. Group : C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000090/2022-2023 | 830/BSD | 23/05/2022 | 22/06/2022 | M/S ASHA CONSTRUCTION | 4.6 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Extension of pipe linefor providing functional house hold tap connection at Sanchra habitation(Part)of MOSAGRAM ZONE-II Piped Water Supply Schemewithin Burdwan Sub-Divn under Burdwan Division,PHE Dte". Group : E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000104/2022-2023 | 987/BSD | 16/06/2022 | 16/07/2022 | MD HASIN | 2.51 | 2.51 | 100 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Construction of Approach P.C.C Road & Circular Soak Well At Head works site of MASAGRAM Zone-II Piped W/S. Scheme at Jamalpur Dev. Block under Burdwan Division, PHE Dte._2ND CALL |  | Junior Engineer, Burdwan Division | ORD/000837/2024-2025 | 966/AE/HQ | 22/11/2024 | 22/12/2024 | SOUMYAVASH DAS | 0.93 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Re-laying of u-PVC Pipeline damaged by Irrigation department at Sanchra village of Masagram Zone-II Piped W/S Scheme at Jamalpur Development Block under Burdwan Division,PHE Dte |  |  | ORD/001130/2023-2024 | 127/BSD | 18/01/2024 | 17/02/2024 | DHIRENDRANATH SOM | 0.85 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Re-laying of UPVC Pipeline(Damaged by Irrigation Department)and repairing damaged FHTC at Masagram Mouza (Habitation) under Masagram Zone-I Piped Water Supply Scheme Jamalpur Development under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000183/2023-2024 | 1007/BSD | 06/06/2023 | 21/06/2023 | DEBASHISH ENTERPRISE | 0.85 | 0.83 | 97.96 | 100
Total | [13 empty] | 147.63 | 177.57 | 120.29