## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Extension of UPVC distribution pipeline in connection with FHTC for Masagram (Zone-I) & adjoining mouzas water supply scheme at Jamalpur Development Block under Burdwan Division, PHE Dte.[Gr.-B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000419/2021-2022 | 1112/BSD | 23/08/2021 | 07/10/2021 | M/S ASHA CONSTRUCTION | 4.71 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Masagram Piped Water Supply Scheme at Habaspur Village, Chouberia Village, Ballabhbati Village & Masagram (4 Nos. habitations), Jamalpur Block under Burdwan Division, PHE Dte. (Agr. No. 710/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000342/2020-2021 | 1578/BWD | 22/02/2021 | 23/04/2021 | MD HASIN | 60.21 | 14.7 | 24.41 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Masagram Piped Water Supply Scheme at Dadpur Village, Sarangpur Village (2Nos. habitations) & Sanchra Village, Jamalpur Block under Burdwan Division, PHE Dte.(Agreement No. 753/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000437/2020-2021 | 1599/BWD | 22/02/2021 | 23/04/2021 | M/S ASHA CONSTRUCTION | 65 | 34.96 | 53.78 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Construction of Boundary Wall at 2nd T/W Site of Masagram Zone-I Water Supply Scheme under Jamalpur Block of Burdwan Division, PHE Dte (Length-50.0 Mtr,Col-17 Nos). Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000443/2021-2022 | 201/BSD | 01/02/2022 | 18/03/2022 | SANDIPAN SENGUPTA | 3.12 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Extension of UPVC distribution pipeline in connection with FHTC for Masagram (Zone-II) and its adjoining mouzas water supply scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. (Habaspur Habitation) [Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000535/2021-2022 | 1206/BSD | 09/09/2021 | 09/10/2021 | MD HASIN | 4.85 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Laying of 200mm.dia. HDPE Distribution pipe line (Node No.118 to 119) for Masagram (Zone-I) & adjoining mouzas Water Supply Scheme at Jamalpur Development block under Burdwan Division,PHE Dte. Group : C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000090/2022-2023 | 830/BSD | 23/05/2022 | 22/06/2022 | M/S ASHA CONSTRUCTION | 4.6 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Extension of pipe linefor providing functional house hold tap connection at Sanchra habitation(Part)of MOSAGRAM ZONE-II Piped Water Supply Schemewithin Burdwan Sub-Divn under Burdwan Division,PHE Dte". Group : E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000104/2022-2023 | 987/BSD | 16/06/2022 | 16/07/2022 | MD HASIN | 2.51 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Construction of Approach P.C.C Road & Circular Soak Well At Head works site of MASAGRAM Zone-II Piped W/S. Scheme at Jamalpur Dev. Block under Burdwan Division, PHE Dte._2ND CALL |  | Junior Engineer, Burdwan Division | ORD/000837/2024-2025 | 966/AE/HQ | 22/11/2024 | 22/12/2024 | SOUMYAVASH DAS | 0.93 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Re-laying of u-PVC Pipeline damaged by Irrigation department at Sanchra village of Masagram Zone-II Piped W/S Scheme at Jamalpur Development Block under Burdwan Division,PHE Dte |  |  | ORD/001130/2023-2024 | 127/BSD | 18/01/2024 | 17/02/2024 | DHIRENDRANATH SOM | 0.85 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Re-laying of UPVC Pipeline(Damaged by Irrigation Department)and repairing damaged FHTC at Masagram Mouza (Habitation) under Masagram Zone-I Piped Water Supply Scheme Jamalpur Development under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000183/2023-2024 | 1007/BSD | 06/06/2023 | 21/06/2023 | DEBASHISH ENTERPRISE | 0.85 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | SM/07815 | Retrofitting | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House, Boundary wall, Land Development and Rising main connection of MASAGRAM (Zone-II) Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE]. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/001042/2023-2024 | 785/BWD | 27/02/2024 | 01/09/2024 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 25.8 | 0 | 0 | 40
Total | [13 empty] | 173.42 | 49.65 | 28.63