## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Jotkrishtai (Jotkestai Habitation), Kalna (Jotkalna Habitation) & Kanshra (Bhabanipur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte.(Agreement no. 571/BWD of 2020-2021) | AE(HQs) |  | ORD/000332/2020-2021 | 441/BWD | 19/01/2021 | 20/03/2021 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 19.48 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Bishnubati (Harekrishnapur Habitation), Jotsubal (Jotsubalpaharpur & Sagar Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement no. 594/BWD of 2020-2021) | AE(HQs) |  | ORD/000330/2020-2021 | 619/BWD | 25/01/2021 | 26/03/2021 | ROY CONSTRUCTION | 20.42 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Kalna (Kalnagram & Surakalna Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 639/BWD OF 2020-2021] | AE(HQs) |  | ORD/000433/2020-2021 | 989/BWD | 04/02/2021 | 05/04/2021 | IJABUL SEKH | 22.09 | 21.45 | 97.1 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Laying of uPVC pipe for providing FHTC at Jorbandh habitation of Kanshra Mouza within Kanshra Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E DTE. [Group: ¿C¿] | AE(HQs) |  | ORD/000226/2021-2022 | 1898/AE/HQ | 16/11/2021 | 16/12/2021 | M/S ANAND CONSTRUCTION | 4.62 | 4.62 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Jotsubal village within Kanshra water supply scheme under Burdwan Division, PHE Dte. [Gr.-A] | AE(HQs) |  | ORD/000866/2020-2021 | 1256/AE/HQ | 15/02/2021 | 17/03/2021 | ROY CONSTRUCTION | 4.84 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Laying of uPVC pipe for providing FHTC at Kanshra Village within KANSHRA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte. [Group : A] | AE(HQs) |  | ORD/000045/2022-2023 | 199/AE/HQ | 06/04/2022 | 06/05/2022 | DEBASHISH ENTERPRISE | 4.84 | 4.84 | 100 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Laying of 90 mm dia UPVC pipe for providing FHTC at Surekalna habitation of Kalna Mouza within Kanshra piped water supply scheme, at Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-D] | AE(HQs) |  | ORD/000752/2021-2022 | 1899/AE/HQ | 16/11/2021 | 16/12/2021 | SWASTIK ENTERPRISE | 4.75 | 4.58 | 96.29 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Laying of 75 mm and 50 mm dia UPVC pipe for providing FHTC at Kalnagram habitation of Kalna Mouza within Kanshra piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-C] | AE(HQs) |  | ORD/000769/2021-2022 | 1857/AE/HQ | 05/10/2021 | 04/11/2021 | SANJAY SK | 3.5 | 2.73 | 78.2 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Paharpur & Chikonhati village within the command area of KANSHRA Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. GROUP : B | AE(HQs) |  | ORD/000228/2022-2023 | 425/AE/HQ | 03/08/2022 | 02/09/2022 | OM ENTERPRISE | 4.1 | 4.1 | 99.88 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Kanshra (Jorbandh & Kanshra Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte.[Agreement No. 625/BWD OF 2020-2021] | AE(HQs) |  | ORD/000438/2020-2021 | 957/BWD | 03/02/2021 | 04/04/2021 | DEBASHISH ENTERPRISE | 21.87 | 21.76 | 99.5 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Kalna village within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : C] | AE(HQs) |  | ORD/000460/2021-2022 | 68/AE/HQ | 11/02/2022 | 13/03/2022 | MAA BHABANI CONSTRUCTION | 4.81 | 4.81 | 100 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Laying of UPVC Pipeline for providing FHTC at Kanshra Mouza (Habitation) under KANSHRA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | AE(HQs) |  | ORD/000067/2023-2024 | 2018/BWD | 28/04/2023 | 28/05/2023 | TARAMA AGENCY | 12.58 | 12.56 | 99.82 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Interconnection between inlet & delivery pipe with main distribution pipeline within command area of KANSHRA Piped W/S. Scheme, Jamalpur Block under Burdwan Division, PHE. Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000826/2022-2023 | 214/AE/HQ | 31/03/2023 | 30/04/2023 | OM ENTERPRISE | 0.87 | 0.83 | 94.92 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Extension of pipeline for KANSHRA Piped Water Supply Scheme at Badalpur Habitation in Jamalpur Block under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000828/2022-2023 | 216/AE/HQ | 31/03/2023 | 30/04/2023 | DEBASHISH ENTERPRISE | 0.95 | 0.95 | 100 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Construction of sluice valve chamber & supply of sluice valve for extension of pipeline for KANSHRA Piped W/S. Scheme, Jamalpur Block under Burdwan Division, PHE. Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000829/2022-2023 | 217/AE/HQ | 31/03/2023 | 30/04/2023 | DEBASHISH ENTERPRISE | 0.92 | 0.92 | 100 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Extension of pipeline for KANSHRA Piped Water Supply Scheme at Natungram Habitation in Jamalpur Block under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000827/2022-2023 | 215/AE/HQ | 31/03/2023 | 30/04/2023 | DEBASHISH ENTERPRISE | 0.95 | 0.95 | 99.71 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | SM/07816 | Retrofitting | Extension of pipeline for KANSHRA Piped Water Supply Scheme at Badalpur & Natungram (Habitation) in Jamalpur Development Block for providing water tap connection (FHTC) under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000406/2023-2024 | 421/AE/HQ | 02/08/2023 | 01/09/2023 | DEBASHISH ENTERPRISE | 0.95 | 0.94 | 98.39 | 100
Total | [13 empty] | 132.55 | 86.03 | 64.9