## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme | SM/07819 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ALIPUR Piped Water Supply Scheme at Debipur, Alipur & Benapur (2 Nos Habitation) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte. [Agreement No. 92/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000423/2020-2021 | 812/BWD | 01/02/2021 | 02/05/2021 | MD HASIN | 90.85 | 18.82 | 20.71 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme | SM/07819 | Retrofitting | Extension of UPVC and HDPE Pipe Line, Providing Left Out FHTC at south part of Debipur rail gate, Land Development & construction of PCC approach Road inside proposed boundary of H/W Site of ALIPUR & its adjacent mouza Water Supply Scheme under MEMARI-I Block of Burdwan Division, PHE Dte. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000287/2024-2025 | 2740/BWD | 12/07/2024 | 30/12/2024 | M/S K.P. CONSTRUCTION | 122.03 | 0 | 0 | 50
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme | SM/07819 | Retrofitting | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for ALIPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001095/2024-2025 | 430/BWD | 20/01/2025 | 03/11/2025 | DULAL MAJUMDER | 117.26 | 0 | 0 | 30
Total | [13 empty] | 330.14 | 18.82 | 5.7