## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001013/2021-2022 | null | 21/01/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001045/2021-2022 | 934/DW | 31/01/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Nandanpur and Rampur village within the command area of Keunta Piped Water Supply Scheme at Raina-II Block under Burdwan Division, PHE Dte. [Group : D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000461/2021-2022 | 69/AE/HQ | 11/02/2022 | 13/03/2022 | SUPER SKILL | 4.16 | 3.85 | 92.5 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000390/2021-2022 | 269/BWD | 14/01/2022 | 13/02/2022 | PRONAB KUMAR DEY | 6.99 | 3.32 | 47.52 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Repairing of damage concrete work due to laying of pipeline at Keunta within Keunta water supply scheme under Burdwan Division, PHE Dte. [Gr.-G] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000556/2021-2022 | 1895/AE/HQ | 16/11/2021 | 16/12/2021 | DUBE ENTERPRISE | 2.39 | 2.27 | 94.98 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Realignment and culvert crossing of D.I. pipeline at damaged section and repairing of uPVC pipeline at Nandanpur, Keunta and Rampur village within Keunta Piped Water Supply Scheme, Raina ¿ II Block under Burdwan Division, PHE. Dte. [Group : D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000043/2022-2023 | 236/AE/HQ | 19/04/2022 | 19/05/2022 | SUPER SKILL | 4.61 | 3.15 | 68.2 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Extension of pipe line for providing Functional Household Tap Connection (FHTC) and construction of sluice valve chamber within the command area of KEUNTA Piped Water Supply scheme, Raina-II Block under Burdwan Division, PHE Dte._Gr-H | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000663/2021-2022 | 138/AE/HQ | 15/03/2022 | 04/04/2022 | SUPER SKILL | 4.81 | 3.63 | 75.47 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KEUNTA Piped Water Supply Scheme at Kalui, Keunta, Kulpukur, Rathtala, Mandarpur, Rampur & Nandanpur habitation, Raina - I Block under Burdwan Division, PHE Dte. (Agreement No. 57/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000443/2020-2021 | 4853/BWD | 04/12/2020 | 04/03/2021 | SUPER SKILL | 95.71 | 49.1 | 51.31 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Pipeline with FHTC for KEUNTA Water Supply Scheme at Kalui village (30 Nos.), Keunta village (30 Nos.), Mandarpur village (30 Nos.), Rampur village (30 Nos.), Nandanpur village (60 Nos.), within Raina-II Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000712/2022-2023 | 855/BWD | 28/02/2023 | 14/04/2023 | DUBE ENTERPRISE | 60.1 | 31.11 | 51.77 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Vehicle bill for the office of the Assistant Engineer, Burdwan Division, PHE Dte. for the month of July'23. |  |  | BILL/00613/2023-2024 | 560/JJM | 24/08/2023 |  | SK.ASFIA | 0.4 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 3692/BWD | 16/07/2021 |  | Resource Division | 12.43 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | SM/07820 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-41J-6795 for the month of June & July2023. |  |  | BILL/01035/2023-2024 | 745/JJM | 11/10/2023 |  | MD HASIN | 0.79 | 0 | 0 | 0
Total | [13 empty] | 1428.36 | 96.44 | 6.75