## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme | SM/07821 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of GHOSH Piped Water Supply Scheme at Andur & Bahapur village (Mouza), Memari ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 577/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000328/2020-2021 | 437/BWD | 24/02/2021 | 26/03/2021 | MAJILA ENTERPRISE | 22.76 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme | SM/07821 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Ghosh Piped Water Supply Scheme at Mondaljana Part (Bajamondaljana, Kashirampur & Mondaljana Habitation), Horirampur & Ghosh Part Village (Mouza) Memari-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000102/2021-2022 | 3781/BWD | 22/07/2021 | 21/08/2021 | KAUSHIK RAY | 20.09 | 20.09 | 99.98 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme | SM/07821 | Retrofitting | Providing FHTC from dist. System within the command area of GHOSH Piped Water Supply Scheme at Kashirampur, Joyampur, Sajina, Ichapur, Purba-Gantar, Andur, Bahabpur & Ghosh (Part) village (Mouza) at Memari-I Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000338/2021-2022 | 25/BWD | 04/01/2022 | 03/02/2022 | MAJILA ENTERPRISE | 36.17 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme | SM/07821 | Retrofitting | Extension of pipeline for GHOSH Piped Water Supply Scheme at Mondaljone (6 Nos), Kashirampur (8 Nos),Total 14 Nos FHTC Work for Sajal Gram(As per Field verification report for Har Ghar Jal Certification within Memari-I Block including leftout household water connection (FHTC) under Burdwan Division,PHE Dte. Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000333/2022-2023 | 1350/BSD | 02/08/2022 | 07/08/2022 | MAJILA ENTERPRISE | 0.97 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme | SM/07821 | Retrofitting | Extension of pipeline for GHOSH Piped Water Supply Scheme at Mondaljona [6 No's], Kashirampur [8 No's],Total 14 No's FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout husehold water tap connection(FHTC) under Burdwan Division, PHE Dte. |  |  | ORD/000644/2022-2023 | 1350-A/BSD | 02/08/2022 | 07/08/2022 | MAJILA ENTERPRISE | 0.97 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme | SM/07821 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000371/2021-2022 | 209/BWD | 11/01/2022 | 10/02/2022 | M/S ANAND CONSTRUCTION | 21.11 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme | SM/07821 | Retrofitting | Re-Laying of damaged pipeline on distribution system for FHTC work for GHOSH Piped Water Supply Scheme at JOY RAMPUR mouza within MEMARI - I BLOCK under Burdwan Division, PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001070/2024-2025 | 104/BSD | 16/01/2025 | 15/02/2025 | N.S. ENTERPRISE | 4.81 | 0 | 0 | 0
Total | [13 empty] | 106.89 | 20.09 | 18.79