## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme | SM/07822 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mondalgram Piped Water Supply Scheme at Mondalgram (10 Nos Habitation) Village (Mouza), Memari-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000111/2021-2022 | 3879/BWD | 27/07/2021 | 25/09/2021 | SUPRIYA RAY | 102.04 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme | SM/07822 | Retrofitting | Extension of UPVC water supply line for Mondalgram and its adjoining mouzas W/S. Scheme within Memari- II Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000614/2021-2022 | 1576/BWD | 16/03/2022 | 15/04/2022 | PAPRI HAZRA | 10.41 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme | SM/07822 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of MONDALGRAM & its adjoining mouzas Piped Water Supply Scheme, Block ? Memari ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000554/2022-2023 | 5196/BWD | 24/11/2022 | 24/12/2022 | ANIRUDDHA FARUQUE | 11.24 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme | SM/07822 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for MONDALGRAM its Adjoining Mouza W/S Scheme, Block -Memari-II within Burdwan Sub-Division, PHE Dte. (Mouza- Untia) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000840/2022-2023 | 508/BSD | 21/03/2023 | 05/05/2023 | NARSAD SAIKH | 3.12 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme | SM/07822 | Retrofitting | Additional quotation for Untia PHE of Augmentation of Mondalgram water supply scheme.[Memo No.-SGA/ADDL/QUOTI, Dated-21/06/23] |  |  | BILL/00239/2023-2024 | 358/JJM | 14/07/2023 | 14/07/2023 | WEST BENGAL BUILDING AND OTHER CONSTRUCTION WORKERS WELFARE FUND | 2.16 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme | SM/07822 | Retrofitting | Quotation of New connection charges at Augmentation of Mondalgram water supply scheme. [Application No.-5003701437] |  |  | BILL/00065/2023-2024 | 152/JJM | 26/05/2023 | 26/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.64 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme | SM/07822 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MONDALGRAM Piped Water Supply Scheme at Bamunia (Part) (4 Nos. Habs.), Bhigobanpur, Halaodharpur (Part) (2 Nos. Habs.), Mondalgram (Part) (10 Nos. Habs.), Saragachi & Malamba Village (Mouza), Memari - II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000479/2021-2022 | 994/BWD | 21/02/2022 | 22/04/2022 | SUPRIYA RAY | 61.24 | 0 | 0 | 70
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme | SM/07822 | Retrofitting | Left out Functional House hold Tap Connection (FHTC) for MONDALGRAM and its adjoining Mouza W/S Scheme, block ¿Memari II within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000773/2022-2023 | 1326/BWD | 22/03/2023 | 21/05/2023 | DEBASHISH ENTERPRISE | 30.33 | 0 | 0 | 35
Total | [13 empty] | 221.17 | 0 | 0