## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhanya Kherur village and Deleypara, Malpara, Mandalpara, Paschimpara & Purba Daspara habitation of Majhergram piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-385/BWD/2020-21) | Assistant Engineer |  | ORD/000257/2020-2021 | 4124/BWD | 16/10/2020 | 15/11/2020 | SUBRATA GUPTA | 4.86 | 9.73 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sihigram village and Adibashipara, Hindupara (Sihigram), Kamarpara & Makarpara habitation of Majhergram piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-605/BWD/2020-21) | Assistant Engineer |  | ORD/000249/2020-2021 | 4125/BWD | 16/10/2020 | 15/11/2020 | N.S. ENTERPRISE | 4.86 | 6.21 | 127.86 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhanya Kherur village and Duleypara, Malpara, Mandalpara, Paschimpara & Purba Daspara Habitation of Majhergram piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer |  | ORD/000607/2020-2021 | 260/BWD | 13/01/2021 | 12/02/2021 | SUBRATA GUPTA | 4.86 | 9.73 | 200 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Majhergram Piped Water Supply Scheme at Sihigram (P) (Paschimpara habs.), Sonagachi (3 Nos. habs.), Majhergram (8 Nos. habs.) & Ganguria (3 Nos. habs), Monteswar Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000639/2020-2021 | 1497/BWD | 18/02/2021 | 19/04/2021 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 57.97 | 74.34 | 128.23 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Extension of 63 mm dia UPVC pipeline to provide house connection to the beneficiaries of Sihigram village of Majhergram water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Sl No.-D] | Assistant Engineer |  | ORD/000859/2020-2021 | 141/KSD | 12/02/2021 | 14/03/2021 | GOUTAM DEY | 3.14 | 2.96 | 94.28 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Continuation work for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sihigram village and Adibasipara, Hindupara (Sihigram), Kamarpara & Makarpara habitation of Majhergram Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿11B¿] | Assistant Engineer |  | ORD/000658/2021-2022 | 1667/BWD | 23/03/2022 | 22/04/2022 | N.S. ENTERPRISE | 4.16 | 3.66 | 88.05 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 26/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Construction of sanitary Latrine and water supply arrangement at Head Work Site of Majhigram Singot piped water supply schemes under Mongalkote Block under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-01] | Assistant Engineer |  | ORD/000593/2021-2022 | 159/KTS | 24/02/2022 | 17/03/2022 | BABUL SK | 1.76 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000125/2021-2022 | 1106/BWD | 26/02/2022 | 26/02/2022 | Resource Division | 44.82 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41J-6795) for the office of the Deputy Superintending Engineer, Central Circle, PHE Dte. for the month of November & December'22. |  |  | BILL/00464/2022-2023 | 1131/JJM | 28/02/2023 | 28/02/2023 | MD HASIN | 0.72 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | SM/07825 | Retrofitting | Restoration of Nepakuli -Baghnapara road from 1.50 km to 2.50 km damaged due to laying of underground water pipe line by PHE with box cutting and Jhama moorum consolidation under Kalna Highway Sub-Division of Burdwan South Highway Division , P.W (Roads) Dte. during the year 2023-2024 |  |  | BILL/00892/2024-2025 | 1025/JJM | 05/10/2024 | 05/10/2024 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 1.74 | 0 | 0 | 0
Total | [13 empty] | 349.91 | 106.63 | 30.47