## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block | SM/07826 | Retrofitting | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of Kulti piped water supply scheme at Chagram village (Chagram habitation), Dakshin Krishnapur village (Krishnapur habitation), Kala village (Anandanagar, Baganpara, Kala & Saklompur habitation), Kulti village (Dhapaspara & Kulti habitation), Dampara village (Dampara habitation) & Kashipur village (Kashipur habitation), Kalna-II Block under Burdwan Division, PHE Dte.[Tr No.-108/SE/CC/20-21] | Assistant Engineer |  | ORD/000405/2020-2021 | 1130/BWD | 09/02/2021 | 10/04/2021 | UMWELT ENGINEER PVT LTD | 103.15 | 31.07 | 30.12 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block | SM/07826 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Kalna ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000476/2021-2022 | 943/BWD | 17/02/2022 | 19/03/2022 | UDYOG CONSTRUCTION | 5.27 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block | SM/07826 | Retrofitting | Restoration work of Singerkone to Pandua Kulti road via badla from 0.00 km to 2.90 km, (in stretches) damaged due to laying of underground water pipe line by PHE with box cutting and Jhama with moorum consolidation under-Kalna Highvway Sub Division of Burdwan South Highway Division, P.W(Roads)Dte. during the year 2023-24. |  |  | BILL/00648/2024-2025 | 825/JJM | 13/09/2024 | 13/09/2024 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.36 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block | SM/07826 | Retrofitting | Different types of works involve in connection with Augmentation of KULTI (SM/16301) Water Supply Scheme, Block Kalna II under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/000235/2024-2025 | 2553/BWD | 04/07/2024 | 01/03/2025 | HAMID SK | 222.11 | 0 | 0 | 80
Total | [13 empty] | 335.89 | 31.07 | 9.25