## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block | SM/07827 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Krishnabati Piped Water Supply Scheme at Bahara (3 Nos Habitation), Chak Bahara (Natungram Habitation), Chandanpur Simuldanga & Krishnabati (2 Nos Habitation) Village (Mouza), Mangalkot Block under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000088/2021-2022 | 3592/BWD | 13/07/2021 | 11/09/2021 | H SAMANTA | 84.33 | 0 | 0 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block | SM/07827 | Retrofitting | NAME OF THE WORK -RESTORATION WORK OF BIDYANAGAR TO VIA DAMODAR PARA TO BOGPUR ROAD,PACKAGE NO-WB-22-27,BLOCK-PURBASTHALI-1,GP-SRIRAMPUR & JAHANNAGAR. |  |  | BILL/00739/2024-2025 | 893/JJM | 25/09/2024 | 25/09/2024 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 5.21 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block | SM/07827 | Retrofitting | Quotation from WBSEDCL for new service connection charges of Krishnabati w/s scheme under Burdwan Division, PHE Dte. (Application No.-5004422952)(Ref. ID-503758136) |  |  | BILL/00902/2024-2025 | 1048/JJM | 30/10/2024 | 30/10/2024 | WBSEDCL | 7.08 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block | SM/07827 | Retrofitting | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 10/08/2025 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block | SM/07827 | Retrofitting | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000181/2024-2025 | 2296/BWD | 20/06/2024 | 26/02/2026 | M/S DATTA ENTERPRISE | 579.85 | 0 | 0 | 2
Total | [13 empty] | 1254.57 | 0 | 0