## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Basuda village and Basuda Habitation of Serua piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I][Gr.-9A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000791/2020-2021 | 4086/BWD | 16/10/2020 | 15/11/2020 | DHIRENDRANATH SOM | 4.87 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Extension of pipeline at "Bamunara & Kumarun & Sakraw" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000335/2021-2022 | 05/DSD | 03/01/2022 | 02/02/2022 | DHIRENDRANATH SOM | 2.98 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Serua Piped Water Supply Scheme at Rajipur, Ratanpur, Serua & Basuda (P) village, Bhatar Block under Burdwan Division, PHE Dte.[Agreement No. 708/BWD OF 2020-2021] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000340/2020-2021 | 1580/BWD | 22/02/2021 | 23/04/2021 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 74.3 | 24.39 | 32.83 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Extension of 180 mm dia pipeline at "Serua" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000331/2021-2022 | 01/DSD | 03/01/2022 | 02/02/2022 | DHIRENDRANATH SOM | 4.82 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Extension of 50 mm dia. pipeline at "Serua-Basuda-Jhujkadanga" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000332/2021-2022 | 02/DSD | 03/01/2022 | 02/02/2022 | DHIRENDRANATH SOM | 1.84 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Extension of pipeline at "Panua, Ratanpur & Rajipur" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000334/2021-2022 | 04/DSD | 03/01/2022 | 02/02/2022 | DHIRENDRANATH SOM | 4.68 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer ,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000389/2021-2022 | 268/BWD | 14/01/2022 | 13/02/2022 | BHARAT CONSTRUCTION | 14.17 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Relaying of distribution main in alternate route for improvement of water supply at Basudha (South Panoa) village within Serua water supply scheme in Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000698/2021-2022 | 6119/BWD | 25/10/2021 | 24/11/2021 | KOUSIK MALLICK | 26.54 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Trial boring at Kumarun for Serua and its Adjoining Mouza Water Supply Scheme within Bhatar Block under Burdwan Division PHE Dte. [Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000314/2022-2023 | 526/DSD | 22/08/2022 | 29/08/2022 | BABA ADHIRA CONSTRUCTION | 0.6 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Trial boring at Serua for Serua and its Adjoining Mouza Water Supply Scheme within Bhatar Block under Burdwan Division PHE Dte. [Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000315/2022-2023 | 527/DSD | 22/08/2022 | 29/08/2022 | BABA ADHIRA CONSTRUCTION | 0.6 | 0 | 0 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Serua Piped Water Supply Scheme at Bamunara village (Bamunara habs), Jhujkadanga village, Kumarun village & Panua (P) village (Panua (P) & Sakra habs), Bhatar Block under Burdwan Division, PHE Dte.[ | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000344/2020-2021 | 1579/BWD | 22/02/2021 | 23/04/2021 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.03 | 22.16 | 41.01 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Restoration and shifting of pipeline, providing sluice valve, Painting and minor repairing of Switch room, Clearing compound premises, making temporary earthen road and repairing of old Valve chamber, Septic tank etc of Serua Piped water supply Scheme , P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman. |  |  | ORD/001417/2024-2025 | 236/DSD | 07/02/2025 | 24/03/2025 | DHIRENDRANATH SOM | 10.43 | 0 | 0 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | SM/07828 | Retrofitting | Construction of Boundary wall, Land Development work at Head work site, Construction of approach road from main road to OHR of SERUA Piped water supply Scheme, P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001341/2024-2025 | 1024/BWD | 21/03/2025 | 19/06/2025 | KALYAN CHOWDHURY | 18.74 | 0 | 0 | 50
Total | [13 empty] | 218.61 | 46.55 | 21.29