## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur High School Kantagorer Par [23 Nos],Total 23 Nos FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification) within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte. Gr.U | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000337/2022-2023 | 1365/BSD | 04/08/2022 | 09/08/2022 | D.M. ENTERPRISE | 0.97 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped water Supply Scheme at Harirambati[7 Nos],Kamalpur[4 Nos],Kole[5 Nos],Mallikapur[2 Nos],Sahanagar[5 Nos]Total 23 Nos FHTC Work for Sajal Gram(As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte.Gr.D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000336/2022-2023 | 1359/BSD | 03/08/2022 | 08/08/2022 | D.M. ENTERPRISE | 0.96 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur Purbo Sansad Dule Para(23 Nos)Total 23 Nos FHTC Work for Sajal Gram(As per Field Verification Report for Har Ghar Jal Certification and praved for Prodhan of Gop Ganter-II G.P. within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte. Gr.V | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000338/2022-2023 | 1366/BSD | 04/08/2022 | 09/08/2022 | D.M. ENTERPRISE | 0.97 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000371/2021-2022 | 209/BWD | 11/01/2022 | 10/02/2022 | M/S ANAND CONSTRUCTION | 21.11 | 13.18 | 62.41 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Harirambati [7 No's], Kamalpur [4 No's], Kole [5 No's] Mallikapur [2 No's], Sahanagar [5 No's]Total 23 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000647/2022-2023 | 1359-A/BSD | 03/08/2022 | 08/08/2022 | D.M. ENTERPRISE | 0.96 | 0.96 | 99.87 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur High School Kantagorer Par [23 Nos] Total 23 No's FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000651/2022-2023 | 1365-A/BSD | 04/08/2022 | 09/08/2022 | D.M. ENTERPRISE | 0.97 | 0.97 | 99.71 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur Purbo Sansad Dule Para[23 No's] Total 23 No's FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000652/2022-2023 | 1366-A/BSD | 04/08/2022 | 09/08/2022 | D.M. ENTERPRISE | 0.97 | 0.97 | 100.17 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Kamalpur Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000785/2023-2024 | 862/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 95.4 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Balidanga Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000786/2023-2024 | 863/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 95.4 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Mallikpur Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000781/2023-2024 | 859/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 95.4 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Sahanagar Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000782/2023-2024 | 860/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 95.4 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Purba Shrirampur Village, Memari - II Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000742/2023-2024 | 837/AE/HQ | 31/10/2023 | 30/11/2023 | MUNSHI JAVEDUR JAMAN | 0.76 | 0.72 | 95.4 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Extension of PVC Water supply line at Koley village for UTTAR RADHAKANTAPUR and its adjoining mouza W/S Scheme Block:Memari-I within Burdwan Sub-Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE,Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/001012/2023-2024 | 120/BSD | 18/01/2024 | 17/02/2024 | A R TRADERS | 0.92 | 0.8 | 87.73 | 98
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | SM/07830 | Retrofitting | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for UTTAR RADHAKANTAPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/001164/2024-2025 | 556/BWD | 05/02/2025 | 06/05/2025 | SANDIP SARKAR | 14.45 | 0 | 0 | 100
Total | [13 empty] | 46.06 | 20.48 | 44.47