## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Amarpur (Amarpur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 572/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000298/2020-2021 | 439/BWD | 19/01/2021 | 20/03/2021 | M/S ANAND CONSTRUCTION | 16.46 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Reshalatpur village and Reshalatpur habitation of SIALI piped water supply scheme within Burdwan Sub-Division, under Burdwan Division, PHE Dte.[Phase-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000694/2020-2021 | 3321/BWD | 18/09/2020 | 18/10/2020 | MUKHERJEE ENTERPRISE | 4.84 | 0.17 | 3.57 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Mudipur (Part), Rasalatpur (Part) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000346/2021-2022 | 58/BWD | 05/01/2022 | 04/02/2022 | BOSE ENTERPRISE | 18.34 | 16.99 | 92.62 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Siali (Math Siali & Siali Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000923/2020-2021 | 1709/BWD | 25/02/2021 | 27/03/2021 | SKILLS AND FACILITY TRAINING INSTITUTE | 18.33 | 17.48 | 95.34 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Ujirpur (Par Ujirpur & Ujirpur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000922/2020-2021 | 1546/BWD | 22/02/2021 | 24/03/2021 | SKILLS AND FACILITY TRAINING INSTITUTE | 18.87 | 18.01 | 95.46 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Reshalatpur village and Reslatpur habitation of Siali piped water supply scheme under Burdwan Division, PHE Dte.[Phase-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000718/2021-2022 | 7089/BWD | 22/12/2021 | 21/01/2022 | MUKHERJEE ENTERPRISE | 3.45 | 3.11 | 90 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Kora (Kora Habitation), Mudipur (Part) (Mudipur (Part) Habitation) & Reshalatpur (Part) (Reshalatpur (Part) Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000642/2020-2021 | 649/BWD | 27/01/2021 | 28/03/2021 | DHIRENDRANATH SOM | 19.53 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Re-alignment of damaged distribution pipeline at different section due to road widening (PWD Deptt.) of SIALI piped water supply scheme at Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-G] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000261/2021-2022 | 667/BSD | 08/06/2021 | 08/07/2021 | RAINBOW CONSTRUCTION | 4.7 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Extension of uPVC distribution pipe line (Node-128 & 136) in regarding FHTC at Par-Ujirpur village from Sura (Zone-II) water supply scheme within Siali W/S scheme at Jamalpur Development Block. under Burdwan Division, PHE Dte. Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000550/2021-2022 | 370/BSD | 02/03/2022 | 01/04/2022 | BHARAT CONSTRUCTION | 3.36 | 2.78 | 82.66 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Extension of pipeline from existing distribution system within the command area of Siali piped water supply scheme at Siali (Math Siali & Siali Habitation) village mouza under Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-E] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000559/2021-2022 | 957/BSD | 23/07/2021 | 22/08/2021 | ELECTRONIC SURVILLANCE | 3.22 | 2.81 | 87.39 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Extension of pipeline for providing functional household tap connection at Reshalatpur (Part) of Siali piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000577/2021-2022 | 1142/BSD | 26/08/2021 | 25/09/2021 | DHIRENDRANATH SOM | 2.49 | 0 | 0 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Extension of pipeline for Providing Functional Household tap connection at Siali Habitation of SIALI Piped Water Supply Scheme under Burdwan Division, P.H.E.Dte. [Group : D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000037/2022-2023 | 243/AE/HQ | 20/04/2022 | 20/05/2022 | BOSE ENTERPRISE | 3.1 | 2.92 | 94.47 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Extension of pipeline from existing distribution system within the command area of Siali piped water supply scheme for FHTC at Ujirpur (Par Ujirpur & Ujirpur Habitation) village mouza under Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000560/2021-2022 | 958/BSD | 23/07/2021 | 22/08/2021 | ELECTRONIC SURVILLANCE | 4.3 | 3.88 | 90.3 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Extension of pipeline (Branch & Sub Branch) from existing distribution system within the command area of Siali piped water supply scheme for FHTC at Mudipur village and Mudipur habitation within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000774/2021-2022 | 1030/BSD | 05/08/2021 | 04/09/2021 | ELECTRONIC SURVILLANCE | 2.16 | 2.14 | 98.84 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Extension of HDPE pipeline for Providing Functional Household Tap Connection at Amarpur Habitation of SIALI Piped Water Supply Scheme under Burdwan Division,P.H.E.Dte. [Group : E] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000039/2022-2023 | 244/AE/HQ | 20/04/2022 | 20/05/2022 | BOSE ENTERPRISE | 4.11 | 4.1 | 99.84 | 1
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Kora (Part) village of Siali piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000309/2021-2022 | 1643/BSD | 14/12/2021 | 13/01/2022 | MUKHERJEE ENTERPRISE | 1.73 | 1.58 | 91.42 | 1
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | SM/07856 | Retrofitting | Providing FHTC for 100% coverage at Muidipur, Ujirpur, Reshalatpur, Kora, Siali & Amarpur Habitation (Village) for SIALI piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000344/2023-2024 | 3033/BWD | 14/07/2023 | 03/04/2024 | ANWESHA CONSTRUCTION | 31.38 | 20.71 | 66 | 100
Total | [13 empty] | 160.38 | 96.7 | 60.29