## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Construction of Boundary wall at 2nd TW site for Chakshanjadi W/S Scheme with in Jamalpur block under Burdwan Div. PHED.(Lenth-78.0mtr & Col.-28nos.) GROUP : F | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000085/2022-2023 | 819/BSD | 20/05/2022 | 04/07/2022 | SOUMYAVASH DAS | 4.06 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 26/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Extension of pipeline including providing FHTC for CHAKSHANJADI Piped Water Supply Scheme at Chalbalpur Habitation for Sajal Gram (As per Field Verification Report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Divn.PHE Dte.Gr.G. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000340/2022-2023 | 1361/BSD | 03/08/2022 | 08/08/2022 | M/S ANAND CONSTRUCTION | 0.95 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Extension of pipeline providing FHTC for CHAKSHANJADI Piped Water Supply Scheme at Chalbalpur Habitation for Sajal Gram(As per Field Verification Report duly signed by Pradhan for Har Ghar Jal Certification)within Jamalpur Block under Burdwan Divn.PHE Dte.Gr.H. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000341/2022-2023 | 1364/BSD | 04/08/2022 | 09/08/2022 | M/S ANAND CONSTRUCTION | 0.96 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chaksanjadi Piped Water Supply Scheme at Jamdaha, Haibatpur, Chalbalpur & Kanakpur Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement no. 791/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000432/2020-2021 | 1795/BWD | 26/02/2021 | 12/04/2021 | M/S GUPTA ENTERPRISE | 40.21 | 39.33 | 97.8 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE/RWS/JAMALPUR | ORD/000345/2021-2022 | 40/BWD | 05/01/2022 | 04/02/2022 | PREMANANDA ROY BISWAS | 22.68 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Laying of interconnection of both the Pump No.1,2 & 3 and distribution main of 250 mm dia along with Byw-Pass arrangement from Over Head Reservoir for Chak Shanjadi piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000925/2020-2021 | 4970/BWD | 10/12/2020 | 09/01/2021 | TIRUPATI ENTERPRISES | 8.98 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Continuation order for supply & delivery of different dia CIDF pipes, sluice valve & fittings for construction of RCC OHR (400 cum capacity) for Chakshanjadi w/s scheme under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000693/2021-2022 | 387/BWD | 20/01/2022 | 09/02/2022 | B.B.C. ENTERPRISE | 15.17 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE/RWS/JAMALPUR | ORD/000592/2021-2022 | 1454/BWD | 11/03/2022 | 10/04/2022 | PREMANANDA ROY BISWAS | 18.83 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Construction of boundary wall at Head works site of CHAKSHANJADI Piped Water Supply Scheme in Jamalpur Block under Burdwan Division, PHE Dte. (Length - 123 Mtr., 46 Nos Column). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000098/2022-2023 | 2743/BWD | 08/06/2022 | 08/07/2022 | MOYAZZEM CONSTRUCTION | 8.12 | 0 | 0 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Construction of Boundary wall at 3rd TW site for Chakshanjadi W/S Scheme with in Jamalpur block under Burdwan Div. PHED.(Lenth-48.0mtr & Col.-19nos.) GROUP : E | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000084/2022-2023 | 818/BSD | 20/05/2022 | 04/07/2022 | M/S PURBASHA | 4.06 | 0 | 0 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000124/2021-2022 | 1107/BWD | 26/02/2022 | 26/02/2022 | Resource Division | 44.82 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | SM/07857 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chaksanjadi Piped Water Supply Scheme at Chaksanjadi & Shambhupur Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 680/BWD OF 2020-2021] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000313/2020-2021 | 1399/BWD | 15/02/2021 | 01/04/2021 | B.B.C. ENTERPRISE | 43.5 | 84.6 | 194.46 | 0
Total | [13 empty] | 433.34 | 123.93 | 28.6