## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shura (Zone-I) Piped Water Supply Scheme at Shura Village (3 Nos. habitations), Chakdihi Village & Shukpur Village, Jamalpur Block under Burdwan Division, PHE Dte. | AE(HQs) |  | ORD/000675/2020-2021 | 1763/BWD | 26/02/2021 | 27/04/2021 | SUKALPA NIRMAN | 83.4 | 26.66 | 31.96 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shura (Zone-II) Piped Water Supply Scheme at Haragobindapur Village, Kubajpur Village, Dhapdhara Village, Sonargoria Village, Sahahosenpur Village & Paikpara Village Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 687/BWD of 2020-2021) | AE(HQs) |  | ORD/000338/2020-2021 | 1324/BWD | 12/02/2021 | 13/04/2021 | M/S PIONEER CONSTRUCTION | 73.63 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Engineer, Headquarters, Burdwan Division, PHE Dte. for the month of September & October'2022. |  |  | VCH/000839/2022-2023 | 766/VEH/22-23 | 22/11/2022 | 22/11/2022 | SK. ASRAFUDDIN | 0.7 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Relaying of UPVC pipe damaged due to construction of guard wall to maintain water supply at different location within command area of SURAH ZONE II PWSS Block Jamalpur under Burdwan Division P.H.E Dte. | AE(HQs) | J.E. 2 BURDWAN,Junior Engineer, Burdwan Division | ORD/000625/2022-2023 | 523/AE/HQ | 29/09/2022 | 29/10/2022 | J. K. CORPORATION | 0.41 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Laying of HDPE pipe for providing FHTC in different habitation of Shura Mouza within Shura Piped Water Supply Scheme (Zone-I), Jamalpur Block under Burdwan Division, P.H.E DTE. [Group: ¿A¿] | AE(HQs) |  | ORD/000225/2021-2022 | 1815/AE/HQ | 21/09/2021 | 21/10/2021 | SUKALPA NIRMAN | 4.79 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Laying of HDPE pipe for underground crossing of river embankment at different section of Shura piped water supply scheme (Zone-II) under Burdwan Division, PHE Dte. [Gr.-A] | AE(HQs) |  | ORD/000414/2021-2022 | 1855/AE/HQ | 05/10/2021 | 04/11/2021 | M/S PIONEER CONSTRUCTION | 4.67 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Laying of rising main for interconnection of Pump House 1 & 2 and distribution main along with bye pass arrangement for Over Head Reservoir for Shura piped water supply scheme (Zone-II) within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-B] | AE(HQs) |  | ORD/000924/2020-2021 | 1226/AE/HQ | 10/02/2021 | 12/03/2021 | M/S UNIT CONSTRUCTION | 4.29 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Laying of HDPE pipeline at Shura, Chakdighi and Shukpur village for providing FHTC within Shura PWSS (Zone-I), Block-Jamalpur under Burdwan Division, PHE Dte._Gr-A | AE(HQs) |  | ORD/000626/2021-2022 | 124/AE/HQ | 04/03/2022 | 19/03/2022 | BANGA NIRMAN | 4.71 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Laying of HDPE pipeline at Dhapdhara village for providing FHTC within SHURA PWSS (Zone-II), Block-Jamalpur under Burdwan Division, PHE Dte._Gr-A | AE(HQs) |  | ORD/000665/2021-2022 | 133/AE/HQ | 11/03/2022 | 31/03/2022 | M/S UNIT CONSTRUCTION | 2.79 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Supply & delivery of different dia. CIDF Pipes, Sluice valve & fittings for construction of RCC OHR (350 cum capacity) for SHURA (ZONE-I) W/S. Scheme under Burdwan Division, P.H.E. Dte. [Group: B] | AE(HQs) |  | ORD/000742/2021-2022 | 165/AE/HQ | 24/03/2022 | 03/04/2022 | BENGAL BUILDERS | 3.08 | 0 | 0 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Laying of rising main for interconnection of Pump House -1 &2 and distribution main alongwith bye-pass arrangement for Over Head Reservoir for Shura piped water supply scheme (Zone-I) within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-A] | AE(HQs) |  | ORD/000929/2020-2021 | 1228/AE/HQ | 10/02/2021 | 12/03/2021 | BENGAL BUILDERS | 4.71 | 0 | 0 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Laying of HDPE pipeline at Sonargoria and Kubajur village for providing FHTC within Shura PWSS (Zone-II), Block-Jamalpur under Burdwan Division, PHE Dte._2ND CALL [Group : F] | AE(HQs) |  | ORD/000050/2022-2023 | 204/AE/HQ | 06/04/2022 | 06/05/2022 | M/S UNIT CONSTRUCTION | 4.81 | 0 | 0 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at leftout area of Chakdighi Gram Panchayat within the command area of SHURA ZONE-I Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. GROUP : C | AE(HQs) |  | ORD/000229/2022-2023 | 426/AE/HQ | 03/08/2022 | 02/09/2022 | D.M. ENTERPRISE | 3.25 | 0 | 0 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Supplying, laying, fitting, fixing of Sluice valve including construction of valve chamber within command area of SURAH ZONE I PWSS Block Jamalpur under Burdwan Division P.H.E Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000626/2022-2023 | 524/AE/HQ | 29/09/2022 | 29/10/2022 | D.M. ENTERPRISE | 0.41 | 0 | 0 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Extension of pipeline for SHURA (Zone-I) Piped W/S. Scheme Total 115 Nos. FHTC work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Jamalpur Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 3 BURDWAN | ORD/000751/2022-2023 | 1185/BWD | 15/03/2023 | 14/04/2023 | SK NUR ALAM | 3.52 | 0 | 0 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Extension of pipeline for SHURA (Zone-II) Piped W/S. Scheme Total 129 Nos. FHTC work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Jamalpur Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | AE(HQs) |  | ORD/000723/2022-2023 | 970/BWD | 03/03/2023 | 02/04/2023 | SANDIPAN SENGUPTA | 4.08 | 0 | 0 | 1
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Beautification work at Head work, 2nd Pump house site of Surah Zone-I PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at (Jamalpur Block) P.W.S.S under Burdwan Division, PHE Dte. |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000549/2024-2025 | 280/RWS | 03/09/2024 | 13/09/2024 | D.M. ENTERPRISE | 0.97 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Beautification work at Head work, 2nd Pump house site of Surah Zone-II PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at (Jamalpur Block) P.W.S.S under Burdwan Division, PHE Dte. |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000550/2024-2025 | 281/RWS | 27/08/2024 | 06/09/2024 | J.K. CORPORATION | 0.97 | 0 | 0 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Extension of pipeline & providing Functional House Tap Connection at leftout portion of SHURA Zone-II W/S Scheme within Jamalpur Block under Burdwan Division, P.H.E Dte. | AE(HQs) | J.E. 2 BURDWAN,Junior Engineer, Burdwan Division | ORD/000571/2023-2024 | 764/AE/HQ | 25/08/2023 | 24/09/2023 | SANDIPAN SENGUPTA | 3.93 | 0 | 0 | 100
20 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near Dhapdhara Uttor Pal Para under SHURA Z-II PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000590/2024-2025 | 742/AE/HQ | 13/09/2024 | 13/10/2024 | J.K. CORPORATION | 0.96 | 0 | 0 | 100
21 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Shifting & Relaying of Damaged UPVC Pipeline at Chakdighi for Construction of Road under "PATHASHREE", SHURA ZONE-I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000627/2024-2025 | 745/AE/HQ | 13/09/2024 | 13/10/2024 | D.M. ENTERPRISE | 0.95 | 0 | 0 | 100
22 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near Dhapdhara Bostom Para under SHURA Z-II PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000591/2024-2025 | 743/AE/HQ | 13/09/2024 | 13/10/2024 | J.K. CORPORATION | 0.94 | 0 | 0 | 100
23 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near Dhapdhara Purba Pal Para under SHURA Z-II PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000592/2024-2025 | 744/AE/HQ | 13/09/2024 | 13/10/2024 | J.K. CORPORATION | 0.96 | 0 | 0 | 100
24 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Laying of different dia UPVC pipeline for providing FHTC work at various places under SHURA ZONE- I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/001028/2023-2024 | 97/AE/HQ | 15/02/2024 | 16/03/2024 | D.M. ENTERPRISE | 0.93 | 0 | 0 | 100
25 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Construction & Installation of Sluice valve & valve Chamber to control the flow of water under SHURA ZONE-I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/001029/2023-2024 | 98/AE/HQ | 15/02/2024 | 16/03/2024 | D.M. ENTERPRISE | 0.76 | 0 | 0 | 100
26 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | SM/07858 | Retrofitting | Shifting & Relaying of Damaged UPVC Pipeline at Chakdighi Baganbari for Construction of Road under "PATHASHREE", SHURA ZONE-I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000628/2024-2025 | 746/AE/HQ | 13/09/2024 | 13/10/2024 | D.M. ENTERPRISE | 0.72 | 0 | 0 | 100
Total | [13 empty] | 215.34 | 26.66 | 12.38