## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block | SM/07859 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mongalkot Piped Water Supply Scheme at Mongalkot (3 Nos Habitation) Village (Mouza), Mongalkot Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000087/2021-2022 | 3598/BWD | 13/07/2021 | 11/09/2021 | S.S. CONSTRUCTION | 115.84 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block | SM/07859 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G/6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of May & June'2022. |  |  | VCH/000646/2022-2023 | 546/VEH/22-23 | 13/09/2022 | 13/09/2022 | M/S MUNMUN DEY | 0.56 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block | SM/07859 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 26/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block | SM/07859 | Retrofitting | Extension and replacement of pipe line from the existing Distribution System within scheme jurisdiction at Mongalkote village under Mongalkote PWSS under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-02] | Assistant Engineer |  | ORD/000154/2022-2023 | 438/KTS | 27/06/2022 | 27/07/2022 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.75 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block | SM/07859 | Retrofitting | Extension and replacement of pipe line from the existing Distribution System within scheme jurisdiction at Mongalkote village under Mongalkote PWSS under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-03] | Assistant Engineer |  | ORD/000155/2022-2023 | 439/KTS | 27/06/2022 | 27/07/2022 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 1.38 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block | SM/07859 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000116/2021-2022 | 1101/BWD | 26/02/2022 | 26/02/2022 | Resource Division | 9.23 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block | SM/07859 | Retrofitting | Vehicle bill (Car No.-WB-04G-7127) for the month of September'2023. |  |  | BILL/01680/2023-2024 | 1041/JJM | 11/12/2023 | 11/12/2023 | PARTHA PRATIM ACHARYA | 0.39 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block | SM/07859 | Retrofitting | Laying of 150 mm dia. D.I distribution pipe line and restoration of drainage system at Mojlish Dighir Par at Mongalkote under MONGALKOTE Piped Water Supply Scheme under Mongalkote Block under Katwa Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000615/2021-2022 | 1577/BWD | 16/03/2022 | 15/04/2022 | ASMA ENTERPRISE | 7.93 | 0 | 0 | 1
Total | [13 empty] | 361.08 | 0 | 0