## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme | SM/07860 | Retrofitting | Pipeline with FHTC for Isufabad Water Supply Scheme at Fagupur village (15 Nos) of Burdwan-I Block, under Burdwan Division, PHE Dte. Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000476/2022-2023 | 1600/BSD | 14/09/2022 | 14/10/2022 | DUBE ENTERPRISE | 3.08 | 2.78 | 90.09 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme | SM/07860 | Retrofitting | Pipeline with FHTC for Isufabad Water Supply Scheme at ISUFABAD village (15 Nos) of Burdwan-I Block, under Burdwan Division, PHE Dte. Gr.J. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000483/2022-2023 | 1607/BSD | 14/09/2022 | 14/10/2022 | DUBE ENTERPRISE | 1.89 | 1.63 | 86.37 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme | SM/07860 | Retrofitting | Extension of pipeline for ISUFABAD Water Supply Scheme at KASIMPUR village within BURDWAN-I Block , under Burdwan Division, PHE Dte.Gr.A | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000473/2021-2022 | 274/BSD | 15/02/2022 | 17/03/2022 | SUPRIYA RAY | 4.98 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme | SM/07860 | Retrofitting | Providing 19 Nos. FHTC at ISHUFABAD & GRAMGORIA village for declaration of SWAJALGRAM under ISHUFABAD Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000152/2024-2025 | 1037/BSD | 10/06/2024 | 10/07/2024 | DEBASHISH ENTERPRISE | 0.91 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme | SM/07860 | Retrofitting | Providing 35 Nos.FHTC at KASHIMPUR village for declearation of SWAJALGRAM under ISHUFABAD Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000296/2024-2025 | 1278/BSD | 12/07/2024 | 26/08/2024 | DUBE ENTERPRISE | 1.64 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme | SM/07860 | Retrofitting | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/01/2026 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
Total | [13 empty] | 322.1 | 4.41 | 1.37