## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ajhapur village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-331/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000168/2020-2021 | 2748/BWD | 10/08/2020 | 09/09/2020 | E-WORLD | 4.92 | 9.84 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Abujhati village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-312/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000167/2020-2021 | 2739/BWD | 10/08/2020 | 09/09/2020 | INDRAJIT MONDAL | 4.92 | 9.84 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ajhapur village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-429/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000172/2020-2021 | 3803/BWD | 08/10/2020 | 07/11/2020 | E-WORLD | 4.92 | 9.84 | 200 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Abujhati village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-456/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000171/2020-2021 | 3740/BWD | 07/10/2020 | 06/11/2020 | INDRAJIT MONDAL | 4.92 | 9.84 | 200 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Providing functional household tap connection from existing distribution system within the command area of Abujhati piped water supply scheme at Napara, Panchshimul & Siromani village Jamalpur Block under Burdwan Division, PHE Dte. (Tr No.-627/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000371/2020-2021 | 954/BWD | 03/02/2021 | 20/03/2021 | KOUSIK MALLICK | 38.9 | 77.15 | 198.34 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of Abujhati piped water supply scheme at Astai, Dastanpur & Keotara village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Tr No.-624/BWD/20-21] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000404/2020-2021 | 955/BWD | 03/02/2021 | 20/03/2021 | BHARAT CONSTRUCTION | 41.04 | 79.36 | 193.38 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Abujhati Piped Water Supply Scheme at Abujhati (Part) (3 Nos Habitation Part) & Ajapur (Part) (Abujhati Part Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. _2ND CALL. [Agreement No. 754/BWD OF 2020-2021] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000412/2020-2021 | 1740/BWD | 25/02/2021 | 11/04/2021 | T.K. BANERJEE & CO. | 34.87 | 70.22 | 201.38 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Extension of pipeline for providing functional household tap connection at Dastanpur & Keotara village (Mouza) of ABUJHATI piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Gr.-D) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000154/2021-2022 | 1091/BSD | 18/08/2021 | 02/10/2021 | BHARAT CONSTRUCTION | 3.36 | 6.69 | 198.98 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of ABUJHATI & its adjoining mouzas Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000544/2022-2023 | 5125/BWD | 21/11/2022 | 21/12/2022 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 11.23 | 10.88 | 96.85 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE/RWS/JAMALPUR | ORD/000345/2021-2022 | 40/BWD | 05/01/2022 | 04/02/2022 | PREMANANDA ROY BISWAS | 22.68 | 7.4 | 32.64 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE/RWS/JAMALPUR | ORD/000592/2021-2022 | 1454/BWD | 11/03/2022 | 10/04/2022 | PREMANANDA ROY BISWAS | 18.83 | 6 | 31.87 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Withdrawing and Relaying of Rising main line and Bullah pilling (60.0 mtr) at HD Works Site (near pond) due to Road widening from 4lane to 6 lane of NH2 at chanage 601+951 and 601+650 of ABUJHATI PWSS to in Jamalpur Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000760/2022-2023 | 1290/BWD | 20/03/2023 | 19/04/2023 | SOUMYAVASH DAS | 5.77 | 5.74 | 99.35 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Improvement of 300cum. OHR (Concreting,Plastering,Primer and Painting) for Abujhati PWSS under Jamalpur Block under Burdwan Division PHE Dte. |  | RWS_JAMALPUR | ORD/000134/2024-2025 | 1015/BSD | 07/06/2024 | 22/07/2024 | DEBASHISH ENTERPRISE | 2.01 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Laying different dia UPVC Pipeline for inter connection of existing FHTC near Kayastyaparan of Abujhati Flyover i.c.w. Road widening from 4 lane to 6 lane of NH-2 at chane 601+9521+960 under ABUIHATI PWSS in jamalpur Block within Burdwan Sub Divn. under Burdwan Division, P.H.E. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001093/2023-2024 | 517/BSD | 13/03/2024 | 12/04/2024 | SOUMYAVASH DAS | 0.89 | 0.88 | 99.09 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | SM/07861 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | AE(HQs),AE(HQs), Burdwan Division, PHE Dte. | Junior Engineer, Burdwan Division | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 20/05/2025 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
Total | [13 empty] | 331.89 | 303.67 | 91.5