## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village and Gureghar habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-440/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000165/2020-2021 | 3332/BWD | 18/09/2020 | 18/10/2020 | KAUSHIK RAY | 4.87 | 4.87 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jarogram village and Jaragram habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-441/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000173/2020-2021 | 3333/BWD | 18/09/2020 | 18/10/2020 | SUPRIYA RAY | 4.87 | 4.87 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jarogram village and Jarogram habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-662/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000259/2020-2021 | 4911/BWD | 08/12/2020 | 07/01/2021 | SUPRIYA RAY | 4.87 | 4.87 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village and Gureghar habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-557/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000260/2020-2021 | 4910/BWD | 08/12/2020 | 07/01/2021 | KAUSHIK RAY | 4.87 | 4.87 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dumo village (Dumo habitation) & Satgoria village (Satgoria habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 07] [Agr. No.721/BWD of 2020-2021] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000376/2020-2021 | 1418/BWD | 18/02/2021 | 05/03/2021 | BRINDABAN KONAR | 4.86 | 4.86 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur village and Madhabpur habitation of MADHABPUR Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿7C¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000847/2020-2021 | 3334/BWD | 18/09/2020 | 18/10/2020 | KAJAL MUKHERJEE | 4.86 | 4.86 | 100 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mirzapur village (Mirzapur habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 10] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000194/2021-2022 | 6189/BWD | 28/10/2021 | 12/11/2021 | JAI MAA DURGA & CO. | 2.19 | 2.19 | 100 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Extension of uPVC pipeline for providing FHTC from existing distribution pipe line system within command area of MADHABPUR (Zone-II) W/S Scheme at Khalerpar under Gureghar village, Jamalpur Development Block under Burdwan Division, PHE Dte". Gr,B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000562/2022-2023 | 2099/BSD | 28/11/2022 | 28/12/2022 | PRATIMA CONSTRUCTION | 0.9 | 0.9 | 99.81 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jargram (Part) village (Jargram (P) habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 05] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000421/2020-2021 | 1416/BWD | 18/02/2021 | 05/03/2021 | LAKSHMIKANTA DAS | 4.86 | 4.86 | 100 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Repairing of damaged 180 mm dia UPVC pipeline at Madhabpur village for Madhabpur water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000844/2020-2021 | 79/BSD | 19/01/2021 | 18/02/2021 | KOUSIK MALLICK | 4.82 | 4.7 | 97.52 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur village and Madhabpur habitation of MADHABPUR Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿7C¿] | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000846/2020-2021 | 7050/BWD | 22/12/2020 | 21/01/2021 | KAJAL MUKHERJEE | 4.86 | 4.49 | 92.21 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Laying of damaged UPVC pipeline with HDPE pipes at Madhabpur village for Madhabpur Zone-I water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-G] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000534/2021-2022 | 1478/BSD | 09/11/2021 | 09/12/2021 | KOUSIK MALLICK | 3.57 | 3.56 | 99.65 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jargram (Part) village (Jargram (P) habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 05] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000027/2022-2023 | 2058/BWD | 19/04/2022 | 04/05/2022 | LAKSHMIKANTA DAS | 4.86 | 4.86 | 100 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Extension of uPVC pipeline regarding FHTC for Gureghar, Dumo, Basantabati habitation under Madhabpur (Zone-II) W/S. Scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000160/2022-2023 | 3139/BWD | 19/07/2022 | 18/08/2022 | PRATIMA CONSTRUCTION | 5.64 | 5.53 | 98.15 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur (Part) village (Madhabpur (P) habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 06] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000458/2020-2021 | 1417/BWD | 18/02/2021 | 05/03/2021 | KAJAL MUKHERJEE | 4.86 | 3.28 | 67.34 | 1
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of MADHABPUR (Z-I) W/S Scheme under Jamalpur Block within Burdwan Sub-Division, PHE Dte. |  |  | ORD/000201/2023-2024 | 2704/BWD | 08/06/2023 | 08/07/2023 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.26 | 12.53 | 94.49 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Preparation and Submission of DPR for Augmentation of MADHABPUR PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000363/2023-2024 | 1525/BSD | 17/07/2023 | 01/08/2023 | CARTO | 0.78 | 0.77 | 99.01 | 100
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village (Gureghar habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A). [SL. No. : 08] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000543/2020-2021 | 1419/BWD | 18/02/2021 | 05/03/2021 | KAUSHIK RAY | 4.87 | 4.87 | 100 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mirzapur village (Mirzapur habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 10] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000536/2020-2021 | 1421/BWD | 18/02/2021 | 05/03/2021 | JAI MAA DURGA & CO. | 4.86 | 4.86 | 100.05 | 0
20 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village (Gureghar habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B). [SL. No. : 09] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000460/2020-2021 | 1420/BWD | 18/02/2021 | 05/03/2021 | SAIKAT RAY | 4.87 | 4.87 | 100 | 0
21 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Extension of pipeline for providing functional household tap connection at Gureghar village of MADHABPUR Zone-II piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000234/2021-2022 | 1128/BSD | 26/08/2021 | 10/10/2021 | SAIKAT RAY | 1.4 | 1.25 | 89.4 | 0
22 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | SM/07862 | Retrofitting | Construction of switch rooms & Rising main at different TW site for MADHABPUR (Zone-I) Piped Water Supply Scheme under Jamalpur Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000532/2023-2024 | 3629/BWD | 21/08/2023 | 20/10/2023 | DEBJYOTI GOSWAMI | 9.11 | 4.79 | 52.55 | 80
Total | [13 empty] | 104.9 | 97.49 | 92.94