## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur Palashi (Part-A) village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-471/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000350/2020-2021 | 241/KTS | 01/10/2020 | 05/10/2020 | CHANCHAL PAL | 1.19 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at KHETIA Pipe Water Supply Scheme of Burdwan -I Block under Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000464/2022-2023 | 3963/BWD | 13/09/2022 | 13/10/2022 | M/S UNIQUE | 6.23 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Khetia Piped Water Supply Scheme at Simdali (P) village (09 Nos. (P) habs), Burdwan-I Block under Burdwan Division, PHE Dte. [Agreement No. 749/BWD OF 2020-2021] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000441/2020-2021 | 1496/BWD | 18/02/2021 | 19/04/2021 | H SAMANTA | 52.6 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | Retrofitting | Providing Functional Household Tap Connection(FHTC)from existing distribution system at Khetia Water Supply Scheme(Habitation-Khetia,Gopalbati,Tentral)of Burdwan-I Block under Burdwan Sub-Division under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000635/2022-2023 | 11/BSD | 06/01/2023 | 21/01/2023 | M/S UNIQUE | 0.92 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Khetia Piped Water Supply Scheme at Gopalbati village, Khetia village (04 Nos. habs) & Tentral village Burdwan-I Block under Burdwan Division, PHE Dte. [Agreement No. 748/BWD OF 2020-2021.] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000442/2020-2021 | 1495/BWD | 18/02/2021 | 04/04/2021 | H SAMANTA | 29.16 | 15.96 | 54.73 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Tentral Village, Burdwan - I Block within Khetia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000733/2023-2024 | 826/AE/HQ | 30/10/2023 | 29/11/2023 | ISHAN CONSTRUCTION | 0.76 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Gopalbati Village, Burdwan - I Block within Khetia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000732/2023-2024 | 825/AE/HQ | 30/10/2023 | 29/11/2023 | ISHAN CONSTRUCTION | 0.76 | 0 | 0 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | Retrofitting | Allied work of interconnection between 2nd TW to distribution line for FHTC work for KHETIA Piped Water Supply Scheme and its adjoining mouzas within BURDWAN-I BLOCK under Burdwan Division, PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000132/2024-2025 | 1016/BSD | 07/06/2024 | 22/07/2024 | ROY CONSTRUCTION | 4.79 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | Retrofitting | KHETIA Piped Water Supply Scheme with Rising Main & Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation at different TW site under BARDHAMAN-I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000874/2023-2024 | 5330/BWD | 04/12/2023 | 29/05/2025 | THE DEVELOPER | 68.62 | 0 | 0 | 56
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | SM/07863 | Retrofitting | Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for NATUNGRAM and KHETIA Piped Water Supply Scheme, Block-Burdwan-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE (RWS) Burdwan-I Block | ORD/001003/2024-2025 | 007/BWD | 02/01/2025 | 01/08/2025 | M/S UNIQUE | 33.59 | 0 | 0 | 80
Total | [13 empty] | 198.62 | 15.96 | 8.04