## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of NABASTHA piped water supply scheme at Begut, Bodhpur, Chakundi, Nabastha & Palsha village, Burdwan-II Block under Burdwan Division, PHE Dte.[Tr No.-65/BWD/20-21] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000385/2020-2021 | 5003/BWD | 10/12/2020 | 10/03/2021 | M/S ASHA CONSTRUCTION | 88.6 | 70.86 | 79.98 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabastha Piped Water Supply Scheme at Saligram (9 Nos Habitation) Village (Mouza), Burdwan-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000040/2021-2022 | 3447/BWD | 29/06/2021 | 29/07/2021 | PAL CONSTRUCTION | 19.73 | 19.19 | 97.25 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Providing FHTC from existing distribution pipe line system within command area of Nabastha Piped W/S. Scheme at Chakundi- Mouza, Bardhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000162/2022-2023 | 3138/BWD | 19/07/2022 | 18/08/2022 | BABUL SK | 11.86 | 12.12 | 102.18 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Construction of boundary wall at Head works site of NABASTHA Piped Water Supply Scheme in Burdwan-II Block under Burdwan Division, PHE Dte. (Length - 154 Mtr., 69 Nos Column). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000097/2022-2023 | 2742/BWD | 08/06/2022 | 08/07/2022 | MOYAZZEM CONSTRUCTION | 10.54 | 10.01 | 94.95 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000416/2021-2022 | 385/BWD | 20/01/2022 | 19/02/2022 | BISWAS ENTERPRISE | 11.97 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Speacial repairing and replace damaged pipe line from Nabastha bus stand to saligram & chakundi village of Nabastha piped water supply scheme at Bardhhaman-II Block under Burdwan Div., PHE Dte.Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000643/2021-2022 | 467/BSD | 21/03/2022 | 20/04/2022 | SETH ENTERPRISE | 4.82 | 4.77 | 99.01 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Providing FHTC in Chakundi, Nabastha & Saligram village for 100% coverage in Sajal Gram from existing distribution system within NABASTHA PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000013/2023-2024 | 1728/BWD | 13/04/2023 | 13/05/2023 | KAUSHIK RAY | 23.96 | 23.87 | 99.61 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Laying of distribution system of different damaged section at Begut, Nabastha & Palsha village regarding smooth running FHTC work within Nabastha PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000136/2023-2024 | 784/BSD | 28/04/2023 | 28/05/2023 | D.M. ENTERPRISE | 0.95 | 0.94 | 98.45 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04H-9111) for the office of the Superintending Engineer, Central Circle, PHE Dte. for the month of December'22 & January'23. |  |  | BILL/00469/2022-2023 | 1116/JJM | 27/02/2023 | 27/02/2023 | SOURAV JANA | 0.8 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41J-6795) for the office of the Deputy Superintending Engineer, Central Circle, PHE Dte. for the month of March to May'23. |  |  | BILL/00461/2023-2024 | 430/JJM | 25/07/2023 | 25/07/2023 | MD HASIN | 1.04 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Preparation and Submission of DPR for Augmentation of Ground Water Based Piped Water Supply Scheme for NABASTHA, Block:Burdwan-II under Burdwan Division, P.H.E Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000987/2024-2025 | 1908/BSD | 28/08/2024 | 12/09/2024 | MEASURE LAND | 0.78 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Laying of interconnection between 4th tube well to OHR for Nabastha Water Supply Scheme within Burdhaman-II Block , under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000807/2022-2023 | 430/BSD | 15/03/2023 | 14/04/2023 | D.M. ENTERPRISE | 0.91 | 0.67 | 74.23 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Providing FHTC for 100% coverage at Palsha (30 nos) & Begut (13nos) and special repairing of Nabastha, Begut & Palsha village for Nabastha Piped W/S scheme , Bardhhaman-II Dev. Block under Burdwan Division, PHE Dte" Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000366/2022-2023 | 1405/BSD | 10/08/2022 | 10/03/2023 | M/S ASHA CONSTRUCTION | 4.71 | 0 | 0 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Different type of works releted at head work side (Internal pathways , Land-Development, repair of pump house and drain) under Nabastha PWSS under Burdwan-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000291/2024-2025 | 1272/BSD | 12/07/2024 | 01/01/2025 | M/S PALASH BISWAS | 4.77 | 4.75 | 99.52 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING LAND DESCRIPTION AT NABASTA PWSS AND OTHER SCHEMES (57Nos) WITHIN BHATAR BLOCK UNDER BURDWAN DIVISION, PHE Dte. |  | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000948/2024-2025 | 1087/DSD | 11/12/2024 | 26/12/2024 | SHANKHA GHOSH | 3.7 | 0 | 0 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Designing,making and erection of Sign Board for SWAJAL GRAM in Khargram village of Burdwan-II Block under Nabastha Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte (5 Nos. Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000446/2025-2026 | 2309/BSD | 19/08/2025 | 29/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Designing, making and erection of Sign Board for SWAJAL GRAM in Karanda village of Burdwan-II Block under Nabastha Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. (5 nos. Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000492/2025-2026 | 2362/BSD | 21/08/2025 | 31/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | SM/07864 | Retrofitting | Designing, making and erection of Sign Board for SWAJAL GRAM in Belut village of Burdwan-II Block under Nabastha Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. (5 nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000493/2025-2026 | 2363/BSD | 21/08/2025 | 31/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
Total | [13 empty] | 191.32 | 147.18 | 76.93