## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Basatpur village of Raipur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿1A¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000679/2020-2021 | 2726/BWD | 10/08/2020 | 09/09/2020 | ASHOK KUMAR GHOSH | 4.92 | 4.92 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Providing FHTC in Purba Kashiara village for 100% coverage in Sajal Gram from existing distribution system within RAIPUR PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000345/2022-2023 | 1368/BSD | 04/08/2022 | 09/08/2022 | ASHOK KUMAR GHOSH | 0.68 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Providing FHTC and extension of UPVC distribution pipeline at Raipur, Gumri, Namalpur & Mahipal habitation for RAIPUR Piped Water Supply Scheme at Burdwan - II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000358/2021-2022 | 104/BWD | 06/01/2022 | 05/02/2022 | ROY CONSTRUCTION | 23.65 | 23.65 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Shifting & Relaying of 2nd T.Well Raising main and providing 5 nos (100mm dia) S/Valve at existing dist. Line for Raipur water supply scheme at Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Group: H | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000481/2022-2023 | 1605/BSD | 14/09/2022 | 14/10/2022 | ASHOK KUMAR GHOSH | 1.72 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Raipur piped water supply scheme at Mahipal (05 Nos Habitation), Purba Kashiara (08 Nos. Habitation), Sahara (04 Nos. Habitation), Sonakur (07 Nos. Habitation), Baratpur (16 Nos, Habitation) & Raipur (10 Nos. Habitation) village, Bardhaman-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000533/2020-2021 | 5007/BWD | 10/12/2020 | 10/03/2021 | ASHOK KUMAR GHOSH | 43.99 | 3.76 | 8.55 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Providing FHTC (12 Nos.) and extension of UPVC distribution pipeline at Basatpur Habitation for Raipur water supply scheme at Burdwan-II Development Block under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000543/2021-2022 | 1461/BSD | 01/11/2021 | 01/12/2021 | ASHOK KUMAR GHOSH | 2.14 | 2.14 | 100 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) of RAIPUR & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. _2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000568/2022-2023 | 5273/BWD | 30/11/2022 | 30/12/2022 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 9.45 | 7.8 | 82.58 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for RAIPUR its Adjoining Mouza W/S Scheme, Block -Bardhaman-II within Burdwan Sub-Division, PHE Dte. (Mouza- PURBA KASHIARA) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000839/2022-2023 | 501/BSD | 21/03/2023 | 05/05/2023 | IRIN CONSTRUCTION CO. | 3.3 | 2.72 | 82.33 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Laying of inter connection between 3rd tube well site and distribution system for Raipur PWSS within Bardhaman-II Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000574/2023-2024 | 2039/BSD | 24/08/2023 | 08/10/2023 | ISHAN CONSTRUCTION | 1.57 | 1.56 | 99.75 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Basatpur Village, Burdwan - II Block within Raipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000776/2023-2024 | 856/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 95.4 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Mahipal Village, Burdwan - II Block within Raipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000775/2023-2024 | 854/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 95.4 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Purba Kashiara Village, Burdwan - II Block within Raipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000778/2023-2024 | 857/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 95.4 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Different type of works related (Internal pathways and approach road 2nd pump, Land-Development, FHTC, repair of boundary wall & pump houses and road restoration) under RAIPUR PWSS under Burdwan-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000374/2024-2025 | 2995/BWD | 01/08/2024 | 01/02/2025 | PRATIVA CONSTRUCTION | 11.79 | 0 | 0 | 80
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | SM/07865 | Retrofitting | Providing Parall LDS (Node- 20 to 24) for smoothly getting water at Baral village within Raipur PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001338/2024-2025 | 1026/BWD | 21/03/2025 | 01/06/2025 | ROY CONSTRUCTION | 8.82 | 0 | 0 | 100
Total | [13 empty] | 114.29 | 48.72 | 42.62