## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Providing Functional Household tap connection from existing distribution system within the command area of Augmentation of Purbasthali piped water supply scheme at Palaspuli village (Mouza), Purbasthali-II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000680/2020-2021 | 993./BWD | 04/02/2021 | 21/03/2021 | IJABUL SEKH | 51.07 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of Purbasthali Piped Water Supply Scheme at Chupi Village (Mouza), Purbasthali-II Block under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer |  | ORD/000681/2020-2021 | 1589/BWD | 22/02/2021 | 08/04/2021 | DHIRENDRA ENGINEERING & CONSTRUCTION | 70.28 | 17.82 | 25.35 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 26/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Extension of different dia UPVC Pipeline (suggested) as per survey of Horizon of Zone-III portion of Surface Based W/S Scheme in Arsenic Affected Areas of Purbasthali - II Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000009/2021-2022 | 3136/BWD | 03/06/2021 | 02/08/2021 | ASHOK KUMAR GHOSH | 34.74 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Extension of different dia UPVC pipeline (suggested) as per survey of Horizon of Zone-I portion of surface based water supply scheme in Arsenic affected areas of Purbasthali-II Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000810/2020-2021 | 826/BWD | 01/02/2021 | 02/04/2021 | DEY NIRMAN | 24.83 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Extension of different dia UPVC pipeline (suggested) as per survey of Horizon of Zone-IV portion of surface Based Water supply scheme in Arsenic affected areas of Purbasthali-II Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000865/2020-2021 | 754/BWD | 29/01/2021 | 30/03/2021 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 20.95 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Construction of Pump House cum chlorine room (3.6 mtr x 3.0 mtr room) without sanitary and water supply arrangement at old Head Work Site of Purbasthali & it's adj. mouzas water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.^ (Sl No-C) | Assistant Engineer |  | ORD/000323/2021-2022 | 986/KSD Dt- 24.09.2021 | 24/09/2021 | 23/11/2021 | SURATH DEY | 2.84 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Laying of different dia UPVC pipe at the balance portion of different section for Augmentation of Purbasthali & its adjoining mouzas water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte.[Part-C][Gr.-C] | Assistant Engineer |  | ORD/000868/2020-2021 | 31/KSD | 11/01/2021 | 25/02/2021 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.68 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Relaying of different dia UPVC pipeline at damaged portion as shown by Horizon of Zone-III of surface based water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL-B] | Assistant Engineer |  | ORD/000959/2020-2021 | 148/KSD | 12/02/2021 | 14/03/2021 | CHANCHAL PAL | 4.82 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Work Order for "Providing Functional house hold tap connections for Sajal Gram Village within Purbasthali-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Purbasthali Aug & Kamalnagar water supply scheme)" |  | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000027/2023-2024 | 346/KSD | 17/04/2023 | 17/05/2023 | RAJESH DAFADAR | 0.88 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Work Order for "Repairing and laying of UPVC pipeline of Majida, Nimdaha, Lakshmipur and Ukhura village for smooth running of FHTC work of Surface Based Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." |  | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000548/2023-2024 | 1303/KSD | 23/08/2023 | 07/09/2023 | PARTHA PRATIM ACHARYA | 1 | 0 | 0 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Hire and labour charges for staging and scaffolding bamboo barricading and removal of rubbish for dismantling capacity 136 Cum of RCC Over Head Reservoir at Purbasthali & it's adj. mouzas water Supply Scheme within Kalna Sub Divison under Burdwan Division , PHE Dte. (Sl No-A) | Assistant Engineer |  | ORD/000327/2021-2022 | 967/KSD Dt-20.09.2021 | 20/09/2021 | 20/10/2021 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.47 | 0 | 0 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000120/2021-2022 | 1111/BWD | 26/02/2022 | 26/02/2022 | Resource Division | 37.62 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-41J-6795 for the month of June & July2023. |  |  | BILL/01035/2023-2024 | 745/JJM | 11/10/2023 | 11/10/2023 | MD HASIN | 0.79 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at balance portion from existing distribution system within the command area of Aug. of PURBASTHALI Piped Water Supply Scheme at Chupi village (Mouza), Purbasthali - II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000028/2022-2023 | 2079/BWD | 20/04/2022 | 20/05/2022 | M/S K.P. CONSTRUCTION | 39.64 | 0 | 0 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Augmentation of Purbasthali piped water supply scheme at Palaspuli village (Mouza), Purbasthali-II Block under burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000587/2020-2021 | 993/BWD | 04/02/2021 | 21/03/2021 | IJABUL SEKH | 51.07 | 31.5 | 61.68 | 0
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | SM/07866 | Retrofitting | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 10/08/2025 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
Total | [13 empty] | 1148.78 | 49.32 | 4.29