## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village and Bandh-O-Tawra & Nunari habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-529/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000166/2020-2021 | 3344/BWD | 18/09/2020 | 18/10/2020 | PAPRI HAZRA | 4.86 | 4.86 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village and Bandh-O-Tawra & Nunari habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-530/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000170/2020-2021 | 4006/BWD | 14/10/2020 | 13/11/2020 | PAPRI HAZRA | 4.79 | 4.79 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village (Iymapara & Mahachanda (Part) habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 01] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000411/2020-2021 | 577/BWD | 25/01/2021 | 09/02/2021 | S. MONDAL | 4.86 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda (Part) village (Aymapara & Mahachanda (P) habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte [SL. No. : 15] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000461/2020-2021 | 1466/BWD | 18/02/2021 | 05/03/2021 | BARABELUN NO.-II G.P. UNEMPLOYED CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.86 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 04] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000202/2021-2022 | 6266/BWD | 02/11/2021 | 17/11/2021 | PAPRI HAZRA | 4.86 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Restoration of damaged flanks during laying of distribution pipe with jhama metal and moorum of Bardhaman Katwa road from Shibpur towards 6th Mile ( From Node 89 -64) of Mahachanda Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte.[SL-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000624/2021-2022 | 165/DSD | 16/03/2022 | 15/04/2022 | PREMANANDA ROY BISWAS | 3.89 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village and Mahachanda habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-527/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000163/2020-2021 | 3343/BWD | 18/09/2020 | 18/10/2020 | BIPLAB SAMANTA | 4.86 | 4.86 | 100 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village and Mahachanda habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. (Tr No.-528/BWD/20-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000164/2020-2021 | 4270/BWD | 03/11/2020 | 03/12/2020 | BIPLAB SAMANTA | 4.86 | 4.86 | 100 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 03] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000203/2021-2022 | 6265/BWD | 02/11/2021 | 17/11/2021 | BIPLAB SAMANTA | 4.86 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Restoration of pipeline at 6-Mile_Shibpur-Dharampur along & across Bardhaman-Katwa Road (SH-7) & providing FHTC at Aimapara (Part), Mahachanda (Part), Shibpur, Dharampur, Nunari (Part) Village (Mouza) under MAHACHANDA Piped W/S. Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000277/2021-2022 | 6934/BWD | 13/12/2021 | 27/01/2022 | PREMANANDA ROY BISWAS | 43.33 | 0 | 0 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mahachanda Piped Water Supply Scheme , Block- Bhatar within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000478/2021-2022 | 97/DSD | 18/02/2022 | 20/03/2022 | BIPLAB SAMANTA | 3.54 | 0 | 0 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Restoration of damaged flanks during laying of distribution pipe with jhama metal and moorum of Bardhaman Katwa road from Shibpur towards 6th Mile ( From Node 89 -64) of Mahachanda Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte.[SL-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000638/2021-2022 | 165/DSD | 16/03/2022 | 15/04/2022 | OM ENTERPRISE | 3.88 | 0 | 0 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Laying of parallel line with 90 mm dia uPVC pipe within Node J8-J-48 and providing air valve for improvement of water supply to FHTC at Twara village within MAHACHANDA and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000467/2022-2023 | 3967/BWD | 13/09/2022 | 13/10/2022 | PAPRI HAZRA | 5.26 | 0 | 0 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village (Shibpur-Dharampur habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 02] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000453/2020-2021 | 578/BWD | 25/01/2021 | 09/02/2021 | PRONAB KUMAR DEY | 4.86 | 0 | 0 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer ,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000389/2021-2022 | 268/BWD | 14/01/2022 | 13/02/2022 | BHARAT CONSTRUCTION | 14.17 | 0 | 0 | 1
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 03] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000454/2020-2021 | 582/BWD | 25/01/2021 | 09/02/2021 | BIPLAB SAMANTA | 4.86 | 4.86 | 100 | 0
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 04] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000459/2020-2021 | 583/BWD | 25/01/2021 | 09/02/2021 | PAPRI HAZRA | 4.86 | 4.84 | 99.46 | 0
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Extension of pipeline at Parhat & Patuna village of Mahachanda and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur (Bardhaman North) Sub Division under Burdwan Division, P.H.E. Dte. (Gr.-C) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000107/2021-2022 | 418/DSD | 02/07/2021 | 01/08/2021 | PAPRI HAZRA | 4.18 | 0 | 0 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Laying of UPVC pipeline in TAWRA Habitation within Mahachanda PWSS WITHIN Durgapur(Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000397/2024-2025 | 622/DSD | 05/08/2024 | 04/09/2024 | MAA MAHAMAYA CONSTRUCTION | 4.54 | 0 | 0 | 100
20 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC for Nunari Village under MAHACHANDA Piped W/S. Scheme, Block Bhatar under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000225/2024-2025 | 2525/BWD | 03/07/2024 | 31/10/2024 | THE BUSINESS ENGINEERS INDIA | 28 | 0 | 0 | 25
21 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in Parhat (Part-B) village of MAHACHANDA piped W/S Scheme within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000938/2023-2024 | 910/DSD | 15/12/2023 | 21/02/2025 | OM ENTERPRISE | 0.96 | 0 | 0 | 100
22 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in Parhat (Part-A) village of MAHACHANDA piped W/S Scheme within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000939/2023-2024 | 911/DSD | 15/12/2023 | 21/02/2025 | OM ENTERPRISE | 0.95 | 0 | 0 | 100
Total | [13 empty] | 166.08 | 29.05 | 17.49