## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nurpur village and Nurpur Habitation of KASHIPUR piped water supply scheme within Durgapur Sub-Division (Bardhaman North) under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000659/2020-2021 | 3971/BWD | 14/10/2020 | 13/11/2020 | THREE MAA ENTERPRISE | 1.21 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur village in Sahebganj habitation of Kashipur piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-361/BWD/2020-21) | AE(HQs) | J.E. 2 BURDWAN | ORD/000266/2020-2021 | 3973/BWD | 14/10/2020 | 13/11/2020 | PREMANANDA ROY BISWAS | 4.84 | 1.2 | 24.8 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nurpur village and Nurpur habitation of Kashipur piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-359/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000267/2020-2021 | 3340/BWD | 18/09/2020 | 18/10/2020 | THREE MAA ENTERPRISE | 4.84 | 1.2 | 24.8 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur village and Sahebganj habitation of Kashipur piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-360/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000312/2020-2021 | 3339/BWD | 18/09/2020 | 18/10/2020 | PREMANANDA ROY BISWAS | 4.84 | 1.2 | 24.8 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Extension of distribution main for providing FHTC at Kashipur Ramgere Adibasipara within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000176/2021-2022 | 602/DSD | 07/10/2021 | 06/11/2021 | THREE MAA ENTERPRISE | 4.82 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Extension of distribution main for providing FHTC at Kashipur Ramgere Adibasipara within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000182/2021-2022 | 619/DSD | 25/10/2021 | 24/11/2021 | THREE MAA ENTERPRISE | 4.82 | 4.82 | 99.93 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sripur village (Sripur Habitation) of Kashipur piped water supply scheme within Durgapur Sub-Division under Burdwan Division, PHE Dte.(Tr No.-718/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000613/2020-2021 | 1439/BWD | 18/02/2021 | 05/03/2021 | ROY BISWAS CONSTRUCTION | 4.5 | 9 | 200 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kashipur Piped Water Supply Scheme at Sripur, (Sripur Habitation), Kashipur (Part) (Kashipur & Sahabganj Part Habitation) Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000003/2021-2022 | 3118/BWD | 02/06/2021 | 02/07/2021 | PREMANANDA ROY BISWAS | 35.02 | 59.31 | 169.37 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur (Part) village (Kashipur habitation) of Kashipur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 18] [Agr. No. 720/BWD of 2020-2021] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000375/2020-2021 | 1441/BWD | 18/02/2021 | 05/03/2021 | PREMANANDA ROY BISWAS | 4.48 | 0.44 | 9.91 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur (Part) village (Sahebganj (P) habitation) of Kashipur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 16] [Agree Ment No.719/BWD of 2020-21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000368/2020-2021 | 1440/BWD | 18/02/2021 | 05/03/2021 | THREE MAA ENTERPRISE | 4.52 | 0.45 | 9.91 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer ,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000389/2021-2022 | 268/BWD | 14/01/2022 | 13/02/2022 | BHARAT CONSTRUCTION | 14.17 | 4.11 | 28.99 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Restoration of damaged pipeline during construction of drain, concrete road etc and making valve chamber at various point at Kashipur village within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. [SL-14] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000886/2022-2023 | 739/DSD | 30/12/2022 | 20/01/2023 | PAPRI HAZRA | 0.87 | 0.86 | 99.64 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Restoration of damaged pipeline of distribution main for construction of drain, concrete road etc at various point at Majhipara village for providing FHTC within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000563/2023-2024 | 652/DSD | 24/08/2023 | 23/09/2023 | ANWESHA CONSTRUCTION | 0.96 | 0.96 | 99.82 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Relaying and restoration of damaged pipeline of distribution main for widening of PWD road and Bridge at Sahebganj Bazar for providing FHTC within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000564/2023-2024 | 653/DSD | 24/08/2023 | 23/09/2023 | ANWESHA CONSTRUCTION | 0.95 | 0.95 | 99.91 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Providing Functional Household Tap Connection (FHTC)from distribution system within the command area of Kashipur water supply scheme at Kashipur Nurpur and Sahebganj village to make its Swajalgram under JAL JIBAN MISSION within Bhatar Block in Purba Bardhanan District undrer Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000398/2024-2025 | 623/DSD | 05/08/2024 | 03/11/2024 | RAM MOHAN MUKHERJEE | 3.15 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | SM/07868 | Retrofitting | Arrangement of drinking water supply by installation of solar submersible pump including TW, LDS, FHTC etc. within command area of KASHIPUR W/S. Scheme, Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000969/2025-2026 | 450/BWD | 10/03/2026 | 08/07/2026 | M/S B.N. GUPTA | 152.79 | 0 | 0 | 0
Total | [13 empty] | 246.77 | 84.5 | 34.24