## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Balgona village and Balgona Habitation of Balgona piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000635/2020-2021 | 4333/BWD | 05/11/2020 | 05/12/2020 | S.S. CONSTRUCTION | 4.86 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Haripur village and Haripur habitation of Balgona piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000697/2020-2021 | 4334/BWD | 05/11/2020 | 05/12/2020 | S.S. CONSTRUCTION | 4.03 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Balgona village and Balgona habitation of Balgona piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000698/2020-2021 | 3347/BWD | 18/09/2020 | 18/10/2020 | S.S. CONSTRUCTION | 4.86 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for BALGONA Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000066/2022-2023 | 2389/BWD | 10/05/2022 | 09/06/2022 | ANIRUDDHA FARUQUE | 9.03 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Balgona Piped Water Supply Scheme at Balgona village (Balgona (P), Patna habs), Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000335/2020-2021 | 1574/BWD | 22/02/2021 | 23/04/2021 | M/S S. CHOUDHURY | 63.94 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Laying of additional pipeline to facilitate FHTC at Patna village of Bolgona and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-11] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000854/2022-2023 | 711/DSD | 30/12/2022 | 29/01/2023 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.09 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Extension of pipeline at Patna village of Bolgona and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-10] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000853/2022-2023 | 710/DSD | 30/12/2022 | 29/01/2023 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.65 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Surging of existing Tube Well at Headwork site for Bolgona Water Supply Scheme , Block - Bhatar, Dist - Purba Barddhaman under Durgapur Sub Division, PHE Dte.[SL-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000623/2021-2022 | 164/DSD | 16/03/2022 | 21/03/2022 | J. K. CORPORATION | 0.54 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Central Drilling | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 120 mtrs. Depth) by utilising Departmental machineries for Balgana W/S Scheme, Bhatar block under Purba Burdwan District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000010/2023-2024 | 63/CDD | 06/04/2023 | 06/05/2023 | C.M. ENTERPRISE | 9.91 | 0 | 0 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | WBSEDCL quotation of Balgona piped water supply scheme under Burdwan Division, PHE Dte. [Ref. ID-503447092] |  |  | BILL/00612/2023-2024 | 713/JJM | 05/10/2023 | 05/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.68 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Placing of pipeline at "Patna and adj" villages of Balgona and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000120/2022-2023 | 333/DSD | 27/06/2022 | 12/07/2022 | R.K. ENTERPRISE | 1.11 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Providing Functional Household Tap Connection (FHTC) by sinking of tube well 250 x 150 mm. dia. (2 Nos.) Constn. of Pump House, Boundary Wall and Land Development within command area of BALGANA & BHATAKUL W/S. Scheme, Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001188/2024-2025 | 596/BWD | 07/02/2025 | 07/06/2025 | M/S S.S. ENTERPRISE | 114.01 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | SM/07871 | Retrofitting | Laying of Rising main in between Tube Well and Distribution Line for PUMP HOUSE 3 (RAIL LINE er dhar ) under BOLGONA PWSS in BHATAR Block under Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. |  |  | ORD/000523/2025-2026 | 1019/DSD | 10/07/2025 | 25/07/2025 | S.S. CONSTRUCTION | 0.82 | 0 | 0 | 0
Total | [13 empty] | 226.55 | 0 | 0