## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001013/2021-2022 | null | 21/01/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001045/2021-2022 | 934/DW | 31/01/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Quotation of new connection charges for Bhatar (Zone-I) water supply scheme. P.H. No.-4 |  |  | BILL/00132/2022-2023 | 942/JJM/22-23 | 09/01/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.67 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell Site for Augmentation of BHATAR (Zone-I) Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000059/2022-2023 | 2240/BWD | 02/05/2022 | 16/06/2022 | AUXILIARY TUBE WELL DRILLERS | 28.54 | 20.72 | 72.59 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bhatar Piped Water Supply Scheme at Kapshar, Bamsor & Belenda (3nos) Village (Mouza) under Burwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000017/2021-2022 | 3301/BWD | 15/06/2021 | 14/08/2021 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 141.14 | 137.29 | 97.27 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bhatar Piped Water Supply Scheme at Bhatar, Kantar, Kulchanda, Kulnagar, Palar, Satkhali & Chandipur (7nos) Village (Mouza) under Burwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000018/2021-2022 | 3300/BWD | 15/06/2021 | 14/08/2021 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 143.17 | 127.59 | 89.12 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Retrofitting of RCC Elevated Reservoir (Capacity 300 cum) by shortcreting, Guniting etc. in connection with Augmentation of Bhatar w/s scheme (Zone-I) under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000963/2020-2021 | 1793./BWD | 26/02/2021 | 12/04/2021 | LAGNAJITA & CO. | 20.57 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Quotation of Bhatar water supply scheme, Zone-II, PHE Dte. [Quotation No.-5003600235/Quot/03, dt.-10/02/2023] |  |  | BILL/00375/2022-2023 | 1168/JJM | 10/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.37 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Bhatar Alinagar for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000292/2021-2022 | 721/DSD | 17/12/2021 | 16/01/2022 | DHIRENDRANATH SOM | 4.69 | 4.68 | 99.87 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Vivekanandapally for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000291/2021-2022 | 720/DSD | 17/12/2021 | 16/01/2022 | DHIRENDRANATH SOM | 2.24 | 2.21 | 98.7 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Extension of uPVC pipe line of LDS at Kalpukur Dakshin Para to Palar Lal para for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-H] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000293/2021-2022 | 722/DSD | 17/12/2021 | 16/01/2022 | DHIRENDRANATH SOM | 1.99 | 1.99 | 99.96 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Bhatar Maldanga road to Kalpukur Purbapar for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000295/2021-2022 | 723/DSD | 17/12/2021 | 16/01/2022 | DHIRENDRANATH SOM | 4.26 | 3.7 | 86.86 | 1
13 | PURBA BARDHAMAN |  | Central Drilling | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 120 mtrs. depth) by utilising Departmental machineries for Bhatar W/S Scheme (Z-II) Bhatar block under Purba bardhaman district, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000002/2023-2024 | 64/CDD | 06/04/2023 | 06/05/2023 | C.M. ENTERPRISE | 9.91 | 8.31 | 83.8 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Providing Left-Out FHTC to Katari Habitation within Bhatar Zone-II PWSS, within Durgapur (Burdwan North) Sub-Division, PHE Dte, under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000381/2023-2024 | 556/DSD | 20/07/2023 | 19/08/2023 | BIPLAB SAMANTA | 3.98 | 3.98 | 99.98 | 100
15 | PURBA BARDHAMAN |  | Central Mechanical | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at Augmentation of Bhatar (Zone - I) (Bamsor) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000934/2022-2023 | 1311/CMD | 22/03/2023 | 21/04/2023 | SRI KRISHNA NIRMAN | 11.88 | 10.93 | 91.96 | 99
16 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Quotation of new service connection charges of Aug. of Bhatar (Zone-II) TW-6 water supply scheme under Burdwan Division, PHE Dte. |  |  | BILL/01338/2023-2024 | 1275/JJM | 18/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.53 | 0 | 0 | 0
17 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Quotation of new service connection charges of Aug. of Bhatar (Zone-II) TW-6 water supply scheme under Burdwan Division, PHE Dte. |  |  | BILL/01338/2023-2024 | 1275/JJM | 18/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.53 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS near rail crossing at Balsidanga for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-8] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000881/2022-2023 | 734/DSD | 30/12/2022 | 20/01/2023 | DHIRENDRANATH SOM | 0.96 | 0 | 0 | 100
19 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Kapshor village for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-2] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000875/2022-2023 | 728/DSD | 30/12/2022 | 20/01/2023 | DHIRENDRANATH SOM | 0.95 | 0.95 | 99.87 | 100
20 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Belenda Purbapara for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-03] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000876/2022-2023 | 729/DSD | 30/12/2022 | 20/01/2023 | DHIRENDRANATH SOM | 0.95 | 0.47 | 49.23 | 100
21 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Bamshor and Belenda Purbapara for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-04] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000877/2022-2023 | 730/DSD | 30/12/2022 | 20/01/2023 | DHIRENDRANATH SOM | 0.96 | 0.96 | 100 | 100
22 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Balsidanga village for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-05] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000878/2022-2023 | 731/DSD | 30/12/2022 | 20/01/2023 | DHIRENDRANATH SOM | 0.89 | 0.44 | 49.94 | 100
23 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Providing Left-Out FHTC to Pallar Habitation within Bhatar Zone-I PWSS, within Durgapur (Burdwan North) Sub-Division, PHE Dte, under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000380/2023-2024 | 555/DSD | 20/07/2023 | 19/08/2023 | TARAMA AGENCY | 4.22 | 2.11 | 50 | 100
24 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Sinking of 200 mm dia River Bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Norja village Block -Bhatar, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000271/2022-2023 | 496/DSD | 12/08/2022 | 02/09/2022 | DHIRENDRANATH SOM | 4.35 | 2.18 | 50 | 100
25 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Providing Left Out FHTC to Area Adjacent to Railway Station within Bhatar Zone-II PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/001106/2023-2024 | 241/DSD | 12/03/2024 | 11/04/2024 | BIPLAB SAMANTA | 0.95 | 0.79 | 82.66 | 100
26 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Quotation from WBSEDCL for load enhancement of Augmentation of Bhatar Zone-II (Kulnagar) w/s scheme for P.H.-6. |  |  | BILL/00173/2024-2025 | null | 16/05/2024 |  | WBSEDCL | 3.57 | 0 | 0 | 0
27 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Providing Left Out FHTC to Sansotosh Sayar Par within Bhatar Zone-II PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/001105/2023-2024 | 240/DSD | 12/03/2024 | 11/04/2024 | BIPLAB SAMANTA | 0.94 | 0.83 | 88.71 | 100
28 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Laying of UPVC pipeline in Katari Habitation within Bhatar Zone- II PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer ,JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/001104/2023-2024 | 239/DSD | 12/03/2024 | 11/04/2024 | BIPLAB SAMANTA | 0.56 | 0.52 | 92.34 | 100
29 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Laying of UPVC pipeline in Pallar habitation (Palar Asram Para South side) with Bhatar Zone-I PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000936/2023-2024 | 908/DSD | 15/12/2023 | 29/01/2024 | TARAMA AGENCY | 0.39 | 0.2 | 49.88 | 100
30 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Laying of UPVC pipeline in Pallar habitation (Palar Asram Para North side) with Bhatar Zone-I PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000934/2023-2024 | 907/DSD | 15/12/2023 | 29/01/2024 | PAPRI HAZRA | 0.8 | 0.77 | 96.28 | 100
31 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | SM/08033 | Retrofitting | Providing Left Out FHTC to Ashram Paschimpara within Bhatar Zone-I PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/001165/2023-2024 | 270/DSD | 15/03/2024 | 14/04/2024 | PAPRI HAZRA | 0.92 | 0.77 | 83.73 | 100
Total | [13 empty] | 1655.86 | 332.39 | 20.07