## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block | SM/08101 | Retrofitting | Construction of boundary wall (Back side of OHR) including land development & Pumping out of water at Pump house no - 1 Site of Nabagram Water Supply Scheme under Jamalpur Dev. Block of Burdwan Division, PHE Dte. (Length -50.00 Mtr, Col-20 Nos). Gr.G. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000659/2021-2022 | 472/BSD | 21/03/2022 | 05/05/2022 | MOHAMMAD ISSA | 3.77 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block | SM/08101 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabagram Piped Water Supply Scheme at Ajhapur (Part) (Masagram Habitation), Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 115/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000440/2020-2021 | 1402/BWD | 15/02/2021 | 16/04/2021 | M/S ASHA CONSTRUCTION | 67.11 | 36.94 | 55.05 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block | SM/08101 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabagram Piped Water Supply Scheme at Ajhapur (Part) (Ajhapur Habitation), Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement no. 116/SE/CC/PHE/Dte of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000470/2020-2021 | 1515/BWD | 19/02/2021 | 20/04/2021 | S.S. CONSTRUCTION | 75.65 | 75.24 | 99.47 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block | SM/08101 | Retrofitting | Providing FHTC for 100% coverage at Nabagram, Basishta Pur, Keliri, Ajhapur & Dattapur Mouza (Village) for NABAGRAM Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | RWS_JAMALPUR | ORD/000570/2023-2024 | 3716/BWD | 24/08/2023 | 23/09/2023 | M/S UNIQUE | 23.77 | 0 | 0 | 50
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block | SM/08101 | Retrofitting | Laying of pipeline for providing FHTC 100% coverage and also construction & installation of Sluice Valve & Valve Chamber to control the flow of water, road restoration work etc. of different Piped W/S Schemes, Block Jamalpur under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000194/2024-2025 | 2488/BWD | 01/07/2024 | 02/01/2026 | M/S NATIONAL CONSTRUCTION | 480.97 | 0 | 0 | 80
Total | [13 empty] | 651.27 | 112.18 | 17.23