## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rayan Piped Water Supply Scheme at Rayan (Part) (Baisnabpara, Bayanpara, Bhotargra, Bhtarpur, DVC Canal, Dakhinpara, Dangapara, Daspara, Dulapara, Durgamandir, Ghatimgore, Gopaldighi & Hatu Dewan (N)) Village (Mouza), Bardhaman-I Block under Burdwan Division, PHE Dte.._2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000099/2021-2022 | 3202/BWD | 09/06/2021 | 08/08/2021 | SUNNY ELECTRIC CO. | 53.1 | 51.27 | 96.56 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rayan Piped Water Supply Scheme at Rayan (Part) (Hatu Dewan(S), Kantai Krishnapur, Katwa Road, KhanPukur, Krishnapur, MadanSayar, Makumpara, Malikpara, Malir Bagan, Muchipara, Muslimpara & Narupara) Village (Mouza), Bardhaman-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000191/2021-2022 | 3143/BWD | 04/06/2021 | 19/07/2021 | S.R. ENTERPRISE | 49.27 | 47.96 | 97.34 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | Retrofitting | Extension of UPVC distribution pipeline sluice valve chamber & concrete work in regarding FHTC for Rayan water supply scheme of Bardhaman-I Development Block under Burdwan Division, PHE Dte.[Gr.-E] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000767/2021-2022 | 1428/BSD | 28/10/2021 | 27/11/2021 | S.R. ENTERPRISE | 4.01 | 4 | 99.84 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of RAYAN Piped Water Supply Scheme at Narayandighi & Sadhanpur (Part) Village (Mouza), Burdwan - I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000340/2021-2022 | 27/BWD | 04/01/2022 | 03/02/2022 | DUBE ENTERPRISE | 30.24 | 30.23 | 99.97 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of RAYAN Piped Water Supply Scheme at Naridaspara and balance portion of Sukantapally, Suryapally, Nari Purbapara & Nasakali (Nari Mouza), Burdwan - I Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000080/2022-2023 | 2558/BWD | 19/05/2022 | 18/06/2022 | SARKAR AGENCY | 41.42 | 41.57 | 100.35 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | Retrofitting | Providing FHTC of distribution pipe line at Nari village(Habitation-Sutradharpara,Adibasipara & Suriyapally)for RAYAN Water Supply Scheme at Bardhhaman-I Development Block under Burdwan Division,PHE Dte.Gr.A | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000030/2022-2023 | 677/BSD | 22/04/2022 | 22/05/2022 | BRINDABAN KONAR | 2.68 | 2.68 | 100 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | Retrofitting | Extension of upvc distribution pipe line, s/valve chamber & conc. Work (Habitation-Belbagan,sutradharpara, Khanpukur & Adibasipara under Nari village) in regarding FHTC for Rayan water supply scheme at Bardhhaman-I Development Block under Burdwan Division, PHE Dte.Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000401/2021-2022 | 70/BSD | 14/01/2022 | 13/02/2022 | BRINDABAN KONAR | 4.64 | 4.32 | 93.01 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | Retrofitting | Laying of interconnection between tube well No 1 to 6 & OHR and OHR to distribution system for RAYAN & Its Adjoing Mouzas Water Supply Scheme within Bardhaman I Dev. Block , under Burdwan Division, PHE Dte.Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000402/2021-2022 | 71/BSD | 14/01/2022 | 13/02/2022 | BRINDABAN KONAR | 4.81 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | Retrofitting | Road restoration work due to FHTC & extension pipeline for different village (Rayan, Naryandighi, Nari Das Para, Krishnapur, Nari & Sukantapally) under RAYAN Piped W/S. Scheme at Burdwan - I Dev. Block under Burdwan Division, PHE. Dte. |  |  | ORD/000593/2023-2024 | 3771/BWD | 29/08/2023 | 28/09/2023 | DURGAPADA MONDAL | 5.97 | 5.92 | 99.32 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | SM/08102 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 4103/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 54.42 | 0 | 0 | 0
Total | [13 empty] | 250.55 | 187.96 | 75.02