## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | SM/08103 | Retrofitting | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 1ST TW Site of SRIRAMPUR & its adjoining mouzas Piped Water Supply Scheme, Block ? Purbasthali ? I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000548/2022-2023 | 5127/BWD | 21/11/2022 | 21/12/2022 | M/S SYCHROTECH INDUSTRY | 8.73 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | SM/08103 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Srirampur Piped Water Supply Scheme at Srirampur (Srirampur & Srirampur East Para Habitation) Village (Mouza), Purbasthali-I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000091/2021-2022 | 3654/BWD | 14/07/2021 | 12/09/2021 | ASHOK KUMAR GHOSH | 102.42 | 84 | 82.01 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | SM/08103 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Srirampur Piped Water Supply Scheme at Srirampur Northpara, Srirampur Southpara & Srirampur Westpara within Srirampur (P) Village (Mouza), Purbasthali-I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000283/2021-2022 | 7002/BWD | 16/12/2021 | 14/02/2022 | HAMID SK | 71.23 | 70.84 | 99.46 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | SM/08103 | Retrofitting | Bypass arrangement of rising main and providing Functional house hold tap connections at Srirampur GP within Purbasthali-I Block under SRIRAMPUR PWSS under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000715/2022-2023 | 889/BWD | 01/03/2023 | 31/03/2023 | JAMALUDDIN SK | 13.01 | 12.88 | 99 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | SM/08103 | Retrofitting | Work order for " Providing Functional house hold tap connections for Sajal Gram Village within Purbasthali-I Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Nadanghat & others scheme) Sl No-7" | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000690/2022-2023 | 103/KSD | 08/02/2023 | 08/03/2023 | MOMINUL ISLAM MONDAL | 0.88 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | SM/08103 | Retrofitting | Laying of additional UPVC pipeline for interconnection with main line to branch line of SRIRAMPUR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000710/2023-2024 | 4522/BWD | 12/10/2023 | 11/11/2023 | JAMALUDDIN SK | 6.16 | 5.78 | 93.78 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | SM/08103 | Retrofitting | NAME OF THE WORK -RESTORATION WORK OF BIDYANAGAR TO VIA DAMODAR PARA TO BOGPUR ROAD,PACKAGE NO-WB-22-27,BLOCK-PURBASTHALI-1,GP-SRIRAMPUR & JAHANNAGAR. |  |  | BILL/00739/2024-2025 | 893/JJM | 25/09/2024 | 25/09/2024 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 5.21 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | SM/08103 | Retrofitting | Different types of works involve in connection with Augmentation of SRIRAMPUR (Zone I & II) (SM/08103), MANGANPUR (SM/13327), KAMALPUR (SM/13453) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000190/2024-2025 | 2429/BWD | 27/06/2024 | 20/10/2025 | S.P. CONSTRUCTION | 500.89 | 128.67 | 25.69 | 2
Total | [13 empty] | 708.53 | 302.17 | 42.65