## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Uttar Rameswarpur village of Nandai Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 4B] | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000035/2021-2022 | 3409/BWD | 25/06/2021 | 25/07/2021 | AURGHA BHATTACHARYA | 4.92 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 26/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nandai Piped Water Supply Scheme at Nandai (Part) (7 Nos Habitation Part), Nagargachhi, Pardupra & Uttar Rameswarpur (Part) Village (Mouza), Kalna-I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000089/2021-2022 | 3599/BWD | 13/07/2021 | 11/09/2021 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 110.43 | 107.33 | 97.19 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of NANDAI Piped Water Supply Scheme at opposite site of railway track at Malatipur, Nagargachhi, Mirjapur, Durgapur habitations, Kalna - I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000002/2022-2023 | 1869/BWD | 05/04/2022 | 05/05/2022 | KOUSIK MALLICK | 51.64 | 49.63 | 96.12 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of BAIDYAPUR (Z-I) PWSS, Block - Kalna - II and NANDAI PWSS, Block - Kalna - I Piped Water Supply Scheme, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. |  |  | ORD/000151/2023-2024 | 2424/BWD | 30/05/2023 | 14/07/2023 | KOUSIK MALLICK | 19.84 | 9.14 | 46.09 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000122/2021-2022 | 1109/BWD | 26/02/2022 | 26/02/2022 | Resource Division | 67.99 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Quotation for new service connection charges at Nandai PWSS [PH No.-V][Ref ID-503434397] |  |  | BILL/01125/2023-2024 | 1086/JJM | 20/12/2023 | 20/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.28 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41J-6795) for the office of the Superintending Engineer, Central Circle, PHE Dte. for the month of January & February'23. |  |  | BILL/00292/2023-2024 | 218/JJM | 06/06/2023 | 06/06/2023 | MD HASIN | 0.79 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Construction of Pump House cum switch room (5.40 mtr x 3.60 mtr) with sanitary arrangement (as per drawing no. PHE/SE/CC/PH/DWG-01/2022-2023) at NANDAI Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000806/2023-2024 | 4820/BWD | 08/11/2023 | 25/10/2024 | SK BADIUZZAMAL | 5.69 | 5.69 | 100 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Work Order for "Laying of pipeline at gap portion of old and new pipeline of Nandai Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division , PHE Dte. " | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000947/2023-2024 | 1714/KSD | 04/12/2023 | 11/12/2023 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.64 | 0.64 | 99.4 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Work Order For "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR NANDAI PWSS & SHIKARPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001144/2023-2024 | 1980/KSD | 09/02/2024 | 19/02/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.33 | 49.89 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Work Order for "Restoration of 350 mm dia DI Rising Main with other allied works in connection with Augmentation of Nandai (SM/08104) Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001188/2023-2024 | 2192/KSD | 15/03/2024 | 30/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 3.3 | 3.14 | 95.13 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Vehicle bill (Car No.-WB-04G-7127) for the month of September'2023. |  |  | BILL/01680/2023-2024 | 1041/JJM | 11/12/2023 | 11/12/2023 | PARTHA PRATIM ACHARYA | 0.39 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | SM/08104 | Retrofitting | Providing FHTC in the left out portion of Natungram, Kutirdanga, Kharinan village along with other ancillary work in order to declare Sajal Gram under the command area of NANDAI PWSS (SM/08104) within Kalna Sub Division under Burdwan Division, PHE. Dte. | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000135/2025-2026 | 1447/BWD | 22/05/2025 | 19/09/2025 | MUKHERJEE ENTERPRISE | 42.77 | 0 | 0 | 0
Total | [13 empty] | 539.34 | 175.91 | 32.61