## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amarun village and Amarun habitation of Amarun piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I][Tr No.-508/BWD/20-21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000383/2020-2021 | 4793/BWD | 03/12/2020 | 02/01/2021 | BHARAT CONSTRUCTION | 4.87 | 9.6 | 197.39 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Arra village and Arrah habitation of Amarun piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000624/2020-2021 | 4989/BWD | 10/12/2020 | 09/01/2021 | M.R. CONSTRUCTION CO. | 4.86 | 9.72 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amarun village and Amarun habitation of Amarun piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-805/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000382/2020-2021 | 3345/BWD | 18/09/2020 | 18/10/2020 | BHARAT CONSTRUCTION | 4.87 | 9.73 | 200 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Arrah village and arrah habitation of AMARUN piped water supply scheme within Durgapur (bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-542/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000252/2020-2021 | 3346/BWD | 18/09/2020 | 18/10/2020 | M.R. CONSTRUCTION CO. | 4.86 | 9.72 | 200 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMARUN (Z-II) Piped Water Supply Scheme at Hanrgram (4 Nos. Habs.), Erachya (6 Nos. Habs.) Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000363/2021-2022 | 7157/BWD | 24/12/2021 | 22/02/2022 | S.S. CONSTRUCTION | 76.46 | 38.46 | 50.3 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMARUN (Z-I & II) Piped Water Supply Scheme at Arra, Amarun, Nawada, Sunur (Part), Eora, Palsona & Bijyapur Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000317/2021-2022 | 7086/BWD | 22/12/2021 | 20/02/2022 | NATIONAL CONSTRUCTION | 85.05 | 80.1 | 94.18 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Relaying for shifting of distribution line at Eora village for construction of Box culvert by PWD Department within Amarun and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000313/2022-2023 | 525/DSD | 22/08/2022 | 06/09/2022 | BHARAT CONSTRUCTION | 0.73 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Hanrgram Khaspara, Chhatipara and Daspara for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[SL-29] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000846/2022-2023 | 708/DSD | 31/12/2022 | 30/01/2023 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.61 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Ramnagar Mouza for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-28] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000870/2022-2023 | 726/DSD | 30/12/2022 | 29/01/2023 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.16 | 0 | 0 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Hanrgram Uttarpara, Majhipukur par and Dulepara for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[SL-30] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000871/2022-2023 | 727/DSD | 30/12/2022 | 29/01/2023 | RAM MOHAN MUKHERJEE | 4.78 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Restoration of damaged pipeline of distribution main for construction of drain, concrete road etc at various point at Sunur, and Amarun village for providing FHTC within Amarun W/S Scheme (Zone-I &II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [SL-17] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000859/2022-2023 | 716/DSD | 30/12/2022 | 29/01/2023 | SAMANTA CONSTRUCTION | 1.93 | 1.91 | 98.86 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Construction of Temporary Approach road to HW site for Augmentation of Amarun (Zone-II ) Piped water supply Scheme , P.H.E Dte. Block:-Bhatar, Dist: Purba Bardhaman. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000136/2022-2023 | 347/DSD | 30/06/2022 | 21/07/2022 | M/S S. CHOUDHURY | 1.04 | 1.04 | 100 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Palsona Mouza for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Phase-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-15] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000857/2022-2023 | 714/DSD | 30/12/2022 | 29/01/2023 | SANDIPAN SENGUPTA | 4.81 | 4.81 | 99.96 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Kubajpur Adibasipara and Erachya for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-26] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000868/2022-2023 | 724/DSD | 30/12/2022 | 29/01/2023 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.58 | 4.58 | 99.87 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Nandanarayanpur and Paschimpara for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-27] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000869/2022-2023 | 725/DSD | 30/12/2022 | 29/01/2023 | BABA ADHIRA CONSTRUCTION | 4.83 | 4.83 | 99.98 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Bijyapur Mouza for providing FHTC of Amarun and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-16] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000858/2022-2023 | 715/DSD | 30/12/2022 | 29/01/2023 | SAMANTA CONSTRUCTION | 4.83 | 4.83 | 99.91 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Sinking of 250 X 150 mm dia Tubewell and Modification to distribution network by making a loop and extension with uPVC pipe to augment the water supply to FHTC at Sunur and Arra village of AMARUN and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/001069/2023-2024 | 1016/BWD | 07/03/2024 | 06/05/2024 | BAMDEB CONSTRUCTION & CO | 34.03 | 34.01 | 99.94 | 80
18 | PURBA BARDHAMAN |  | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | SM/08105 | Retrofitting | Extension of UPVC Pipe Line at Sunur and Arra village of AMARUN and its adjoining Mouzas W/S Scheme( Zone-1) village Under Durgapur Sub Division , Under Burdwan Division PHE Dte |  | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000314/2025-2026 | 1063/DSD | 24/07/2025 | 23/08/2025 | BAMDEB CONSTRUCTION & CO | 4.92 | 0 | 0 | 100
Total | [13 empty] | 256.21 | 213.32 | 83.26