## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | SM/08699 | Retrofitting | Extension of pipeline for Chhotobainan water supply scheme at Pahalanpur and Rupsara village within Raina-II Block under Burdwan Division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000418/2021-2022 | 1119/BSD | 24/08/2021 | 08/10/2021 | BOSE ENTERPRISE | 4.67 | 2.43 | 52.07 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | SM/08699 | Retrofitting | Quotation of new connection charges of Chhotobainan water supply scheme under Burdwan Division, PHE Dte. [Application No.-5003481960, Ref ID-503178571], |  |  | VCH/000593/2022-2023 | 709/DW/22-23 | 21/10/2022 | 21/10/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.37 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | SM/08699 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001013/2021-2022 |  | 21/01/2022 | 21/01/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | SM/08699 | Retrofitting | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001045/2021-2022 | 934/DW | 31/01/2022 | 31/01/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | SM/08699 | Retrofitting | Extension of pipeline with FHTC for CHHOTOBAINAN Piped Water Supply Scheme (Akina (P), Pahalanpur, Dakshin Gopalpur, Bajekumarpur, Binodpur, Momrejpur village) within Raina II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000032/2022-2023 | 2163/BWD | 26/04/2022 | 10/06/2022 | BRINDABAN KONAR | 71.69 | 56.07 | 78.21 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | SM/08699 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000390/2021-2022 | 269/BWD | 14/01/2022 | 13/02/2022 | PRONAB KUMAR DEY | 6.99 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | SM/08699 | Retrofitting | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for CHHOTOBAINAN Piped Water Supply Scheme, Block - Raina - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000055/2022-2023 | 2233/BWD | 29/04/2022 | 29/05/2022 | J. K. CORPORATION | 10.76 | 9.72 | 90.3 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | SM/08699 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 3rd Tube Well Site (Baje Kumarpur) to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for Chhotobainan its Adjoining Mouza W/S Scheme, block -Raina-II within Burdwan Sub-Division, PHE Dte. Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000469/2022-2023 | 1526/BSD | 05/09/2022 | 04/11/2022 | BRINDABAN KONAR | 3.03 | 2.6 | 86.04 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | SM/08699 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 424/BWD | 20/01/2022 | 20/01/2022 | Resource Division | 5.5 | 0 | 0 | 0
Total | [13 empty] | 1341.98 | 70.83 | 5.28