## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08700 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sultanpur Piped Water Supply Scheme at Halbele, Hridaypur, Isabpur, Nowapara & Uplati Village (Mouza), Kalna ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 56/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer |  | ORD/000124/2020-2021 | 4901/BWD | 07/12/2020 | 07/03/2021 | MAJILA ENTERPRISE | 94.67 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08700 | Retrofitting | Protection work of distribution system (200 mm dia) of 35 Mtr length near the head work site (Right Side) of Sultanpur & its adjoining mouzas water supply scheme by UC Bullah including Drum Sheet within Kalna Sub-Division under Burdwan Division, PHE Dte.[Gr.-E] | Assistant Engineer |  | ORD/000845/2020-2021 | 20/KSD | 07/01/2021 | 06/02/2021 | DEBASHISH ENTERPRISE | 0.75 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08700 | Retrofitting | Extension of different dia UPVC pipeline at different section of village Upalati, Hridaypur, Gopalpur, Sultanpur & Hatbele to cover up the uncovered habitation of Sultanpur PWSS within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000244/2021-2022 | 6122/BWD | 26/10/2021 | 25/11/2021 | MAJILA ENTERPRISE | 14.34 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08700 | Retrofitting | Providing FHTC in each household from dist. System within Scheme jurisdiction in Hridaypur, Upalati, Belerhat, Gopalpur, Sultanpur, Isabpur & Naopara Village of SULTANPUR W/S. Scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000584/2021-2022 | 1357/BWD | 09/03/2022 | 08/04/2022 | TAPAS KUMAR ROY | 16.69 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08700 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of December22 to February'23. |  |  | BILL/00118/2023-2024 | 30/JJM | 19/04/2023 | 19/04/2023 | PARTHA PRATIM ACHARYA | 1.19 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08700 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000335/2024-2025 | 3015/BWD | 05/08/2024 | 04/10/2024 | HORIZEN | 29.6 | 0 | 0 | 10
Total | [13 empty] | 157.23 | 0 | 0