## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08702 | Retrofitting | Laying of 100 mm dia D.I Pipe for Road widening from 4 lane to 6 lane of NH2 at chainage 596+286 & 596+086 & 596+ 486 at Amra Water supply within Jamalpur Block,under Burdwan Division,PHE Dte". Group : A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000101/2022-2023 | 982/BSD | 16/06/2022 | 16/07/2022 | DEY NIRMAN | 2.89 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08702 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amra Piped Water Supply Scheme at Amra (2 Nos Habitation Part) & Dogachia Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._3rd CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000008/2021-2022 | 3138/BWD | 03/06/2021 | 18/07/2021 | D.M. ENTERPRISE | 57.42 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08702 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMRA Piped Water Supply Scheme (Vill-Dogechia, Habitation- Dogechia ) at Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte.Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000386/2021-2022 | 57/BSD | 13/01/2022 | 12/02/2022 | DEY NIRMAN | 4.81 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08702 | Retrofitting | Extension of pipeline at AMRA water supply scheme at different villages (Tengaberia, Badpur & Kolupukur) FHTC of Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000561/2021-2022 | 1374/BSD | 05/10/2021 | 04/11/2021 | D.M. ENTERPRISE | 4.74 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08702 | Retrofitting | Construction of Boundary wall at 3rd Tube well site of Dogachia Mouza of Amra water supply scheme under Jamalpur block under Burdwan Division, PHE Dte. [Length-59 Mtr][Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000557/2021-2022 | 1028/BSD | 05/08/2021 | 19/09/2021 | MUKHERJEE ENTERPRISE | 4.45 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08702 | Retrofitting | Construction of concrete road and rest portion of boundary wall at Head works site of AMRA Piped Water Supply Scheme in Jamalpur Block under Burdwan Division, PHE Dte. (Length - 122 Mtr., 45 Nos Column). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000146/2022-2023 | 3100/BWD | 14/07/2022 | 13/08/2022 | CHAUDHURI ENTERPRISE | 7.68 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08702 | Retrofitting | Repairing and replace of damaged UPVC Pipeline with installation and construction of valve chamber for control of water flow within command area of AMRA Piped W/S Scheme at Dogachia habitation,Jamalpur Development Block under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000806/2022-2023 | 429/BSD | 15/03/2023 | 14/04/2023 | DEY NIRMAN | 0.89 | 0 | 0 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08702 | Retrofitting | Providing FHTC for Dogachia Mouza [(Habitation (Village)] for AMRA piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000068/2023-2024 | 2019/BWD | 28/04/2023 | 28/05/2023 | DEY NIRMAN | 20.61 | 0 | 0 | 100
Total | [13 empty] | 103.49 | 0 | 0