## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Functional Household Tap Connection (FHTC) at Baratikra village within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. (Part-A). | AE(HQs) | JE/RWS/JAMALPUR | ORD/000167/2021-2022 | 1858/AE/HQ | 05/10/2021 | 04/11/2021 | J. K. CORPORATION | 4.83 | 4.83 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Baratikra village within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. (Part-B). | AE(HQs) | JE/RWS/JAMALPUR | ORD/000168/2021-2022 | 1859/AE/HQ | 05/10/2021 | 04/11/2021 | INDRAJIT MONDAL | 4.83 | 4.83 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Laying of HDPE pipeline at Antpara village for dedicated water supply at Dakshinmohonpur village within Antpara PWSS, Block-Jamalpur under Burdwan Division, PHE Dte. [Group : A] | AE(HQs) | JE/RWS/JAMALPUR | ORD/000455/2021-2022 | 65/AE/HQ | 11/02/2022 | 13/03/2022 | SUPER SKILL | 4.68 | 4.68 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Continuation work order for functional household tap connection (FHTC) at Baratikra village within the command area of Antpara piped water supply scheme at Jamalpur Block under Burdwan Division, PHE Dte.[Part-A][Gr.-D] | AE(HQs) | JE/RWS/JAMALPUR | ORD/000790/2021-2022 | 1950/AE/HQ | 22/12/2021 | 21/01/2022 | J. K. CORPORATION | 4.73 | 4.73 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of May & June'22. |  |  | VCH/000494/2022-2023 | 462/VEH/22-23 | 29/08/2022 | 29/08/2022 | MD HASIN | 0.51 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of ANTPARA & its adjoining mouzas Piped Water Supply Scheme, [Nandanpur Vill.] Block ? Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. _2ND CALL. | AE(HQs) | JE/RWS/JAMALPUR | ORD/000566/2022-2023 | 5275/BWD | 30/11/2022 | 30/12/2022 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 9.45 | 9.44 | 99.92 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Dakshin Mohonpur & Uttar Mohanpur habitation under Antpara water supply scheme under Burdwan Division, PHE Dte. | AE(HQs) | JE/RWS/JAMALPUR | ORD/000586/2020-2021 | 1244/AE/HQ | 12/02/2021 | 14/03/2021 | DIBAKAR SHAW | 4.81 | 1.49 | 30.92 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Antpara habitation within the command area of Antpara water supply scheme under Burdwan Division, PHE Dte. | AE(HQs) | JE/RWS/JAMALPUR | ORD/000567/2020-2021 | 1258/AE/HQ | 15/02/2021 | 17/03/2021 | WESTERN WATER SUPPLY AGENCY | 4.8 | 1.46 | 30.49 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Construction of sluice valve chamber and extension of pipeline for making functional of Household Tap at Daspur village within Antpara piped water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | AE(HQs) | JE/RWS/JAMALPUR | ORD/000325/2021-2022 | 1728/AE/HQ | 25/08/2021 | 24/09/2021 | J. K. CORPORATION | 1.64 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE/RWS/JAMALPUR | ORD/000345/2021-2022 | 40/BWD | 05/01/2022 | 04/02/2022 | PREMANANDA ROY BISWAS | 22.68 | 0 | 0 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Construction of different dia. Sluice Valve chamber to operate water flow for supplying water in zonal demand basis within command area of Antpara PWSS under Burdwan Division, PHE Dte._Gr-C | AE(HQs) | JE/RWS/JAMALPUR | ORD/000628/2021-2022 | 125/AE/HQ | 04/03/2022 | 19/03/2022 | SUPER SKILL | 4.81 | 4.81 | 100 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Laying of uPVC pipe for providing FHTC at Baratikra Village within ANTPARA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte. [Group : C] | AE(HQs) | JE/RWS/JAMALPUR | ORD/000036/2022-2023 | 242/AE/HQ | 20/04/2022 | 20/05/2022 | J. K. CORPORATION | 4.58 | 4.39 | 95.93 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Repairing and restoration of pipeline besides river bank of Damodar damaged due to construction of retaining wall at Antpara to Dakshinmohanpur within command area of ANTPARA PWSS under Burdwan Division, PHE Dte._Gr-B | AE(HQs) | JE/RWS/JAMALPUR | ORD/000661/2021-2022 | 134/AE/HQ | 11/03/2022 | 31/03/2022 | SUPER SKILL | 4.18 | 0 | 0 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE/RWS/JAMALPUR | ORD/000592/2021-2022 | 1454/BWD | 11/03/2022 | 10/04/2022 | PREMANANDA ROY BISWAS | 18.83 | 0 | 0 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ramkrishnapur village (Ramkrishnapur Habitation) of Antpara piped water supply scheme within Head Quarters under Burdwan Division, PHE Dte.[Part-A] | AE(HQs) | JE/RWS/JAMALPUR | ORD/000950/2020-2021 | 1083/BWD | 08/02/2021 | 23/02/2021 | DIBAKAR SHAW | 4.78 | 4.77 | 99.83 | 1
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Laying of uPVC pipe for providing FHTC at Dakshinmohanpur habitation within ANTPARA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-C | AE(HQs) | JE/RWS/JAMALPUR | ORD/000664/2021-2022 | 145/AE/HQ | 16/03/2022 | 05/04/2022 | MUKHERJEE ENTERPRISE | 4.75 | 4.68 | 98.4 | 1
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Antpara village within the command area of ANTPARA Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : A] | AE(HQs) | JE/RWS/JAMALPUR | ORD/000034/2022-2023 | 240/AE/HQ | 20/04/2022 | 20/05/2022 | N.S. ENTERPRISE | 4.77 | 3.69 | 77.23 | 1
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Laying of distribution system of different damaged section at Chakundi & Saligram village regarding smooth running FHTC work within Nabastha PWSS, Bardhhaman II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000138/2023-2024 | 787/BSD | 28/04/2023 | 28/05/2023 | D.M. ENTERPRISE | 0.97 | 0.95 | 98.44 | 100
19 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Laying of UPVC Pipeline at Daspur Habitation under ANTPARA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000409/2023-2024 | 416/AE/HQ | 01/08/2023 | 31/08/2023 | J K CORPORATION | 0.96 | 0 | 0 | 100
20 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Re-Laying of UPVC Pipeline (Damaged by Irrigation Department) at Dakshin Mohanpur Habitation under ANTPARA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000407/2023-2024 | 400/AE/HQ | 28/07/2023 | 27/08/2023 | J K CORPORATION | 0.96 | 0 | 0 | 100
21 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Laying UPVC (Damaged By Irrigation Department) pipeline at Uttar Mohanpur habitation, ANTPARA Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/001072/2023-2024 | 168/AE/HQ | 07/03/2024 | 06/04/2024 | J.K. CORPORATION | 0.92 | 0 | 0 | 100
22 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near RAMKRISHNAPUR MONDAL PARA under ANTPARA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000588/2024-2025 | 740/AE/HQ | 13/09/2024 | 13/10/2024 | J.K. CORPORATION | 0.96 | 0 | 0 | 100
23 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Laying of UPVC (Damaged By Irrigation Department) pipeline at Daspur & Uttar Mohanpur habitation, ANTPARA Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/001071/2023-2024 | 167/AE/HQ | 07/03/2024 | 06/04/2024 | J.K. CORPORATION | 0.82 | 0 | 0 | 100
24 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Laying of UPVC (Damaged By Irrigation Department) pipeline near Baratikra Bridge including construction of new valve chamber under ANTPARA Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/001073/2023-2024 | 169/AE/HQ | 07/03/2024 | 06/04/2024 | J.K. CORPORATION | 0.84 | 0 | 0 | 100
25 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near RAMKRISHNAPUR MUSLIM PARA under ANTPARA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000589/2024-2025 | 741/AE/HQ | 13/09/2024 | 13/10/2024 | J.K. CORPORATION | 0.95 | 0 | 0 | 100
26 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | AE(HQs),AE(HQs), Burdwan Division, PHE Dte. | Junior Engineer, Burdwan Division | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 20/05/2025 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
27 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Re-Laying of U-PVC (Damaged by Irrigation Department) pipeline near Uttar Mahanpur to Dakhin Mahanpur under ANTPARA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) |  | ORD/000027/2025-2026 | 1299/BWD | 28/04/2025 | 27/07/2025 | GOUTAM KUMAR MITRA | 9.64 | 0 | 0 | 0
28 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Laying of uPVC pipe for providing FHTC at Nandanpur Village within ANTPARA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-D | AE(HQs) | JE/RWS/JAMALPUR,Junior Engineer, Burdwan Division | ORD/000666/2021-2022 | 146/AE/HQ | 16/03/2022 | 31/03/2025 | MUNSHI JAVEDUR JAMAN | 4.75 | 0 | 0 | 100
29 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dakshin Mohanpur village (Dakshin Mohanpur Habitation) of Antpara piped water supply scheme within Head Quarters under Burdwan Division, PHE Dte. | AE(HQs) | JE/RWS/JAMALPUR,Junior Engineer, Burdwan Division | ORD/000951/2020-2021 | 4691/BWD | 20/01/2021 | 09/04/2023 | DIBAKAR SHAW | 4.86 | 4.08 | 83.92 | 100
30 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08703 | Retrofitting | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC and 2 Nos. 5000 Ltr. PVC tank installation with construction of RCC structure for ANTPARA Piped W/S. Scheme, Block Jamalpur under Burdwan Division, PHE Dte. | AE(HQs) | JE/RWS/JAMALPUR,Junior Engineer, Burdwan Division | ORD/001082/2023-2024 | 1085/BWD | 12/03/2024 | 26/11/2024 | HI-LIGHT ELECTRONICS | 16.31 | 0 | 0 | 40
Total | [13 empty] | 285.25 | 58.83 | 20.62