## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila Habitation) of Bagila piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Part-A)[SL NO.-08] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000745/2020-2021 | 587./BWD | 25/01/2021 | 09/02/2021 | PAL CONSTRUCTION | 4.86 | 4.86 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of BAGILA Piped Water Supply Scheme at Kiskinda (2 nos Hab), Krishnapur, Talchini & Bagila (Part) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000149/2021-2022 | 4659/BWD | 10/09/2021 | 09/11/2021 | HAMID SK | 60.69 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Extension of pipe line for BAGILA Piped Water Supply Scheme at Krishnapur,Baharampur,Kiskindha,Taktipur in Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte.Group : A | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000102/2022-2023 | 983/BSD | 16/06/2022 | 16/07/2022 | A R TRADERS | 4.83 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila Habitation) of Bagila piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Part-B)[SL NO.-09] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000746/2020-2021 | 585./BWD | 25/01/2021 | 09/02/2021 | HAMID SK | 4.87 | 4.87 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Extension of pipeline for BAGILA Water Supply Scheme at (Baharampur, Taktipur, Krishnapur & Kiskinda North East) village within Memari I Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000669/2021-2022 | 1708/BWD | 25/03/2022 | 24/04/2022 | A R TRADERS | 27.27 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for BAGILA Piped Water Supply Scheme, Block - Memari - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte._ 2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000257/2022-2023 | 3503/BWD | 10/08/2022 | 09/09/2022 | MUNSHI ENTERPRISE | 10.18 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Emergency repaired cleaning of chokage AC Pipeline for (Retrofittins) for BAGILA Piped water supply scheme at Baharampur, Takipur & Kiskinda village for smooth drinking water supply (FHTC) within Memari-I Block under Burdwan Division, PHE Dte. Gr.A | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000561/2022-2023 | 1918/BSD | 11/11/2022 | 26/11/2022 | A R TRADERS | 0.93 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Sinking of additional tube well 250 x 200 mm dia Tube well 150 mtr depth by D.R. Rig method using upvc pipe (CD) and fibre glass strainer for Bagila piped water supply scheme (2nd tube well site), Block-Memari-I under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001312/2020-2021 | 1494/BWD | 18/02/2021 | 20/03/2021 | C.M. ENTERPRISE | 8.68 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Preparation and Submission of DPR for Augmentation of Ground Water Based Piped Water Supply Scheme for MAHESHDANGA, Block:Memari-I under Burdwan Division, P.H.E Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000988/2024-2025 | 1909/BSD | 28/08/2024 | 12/09/2024 | CARTO | 0 | 0 | NAN | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila habitation) of Bagila Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 09] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000042/2021-2022 | 3465/BWD | 29/06/2021 | 14/07/2021 | HAMID SK | 4.87 | 4.87 | 100 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila habitation) of Bagila Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 08] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000034/2021-2022 | 3406/BWD | 25/06/2021 | 10/07/2021 | PAL CONSTRUCTION | 4.86 | 4.86 | 100 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Restoration of Pump House at Head Work site of BAGILA Piped water supply scheme at Memari-I Block under Burdwan Division, Dist.-Purba Bardhaman | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000126/2024-2025 | 1006/BSD | 06/06/2024 | 06/07/2024 | A.R. TRADERS | 0.96 | 0 | 0 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | MAINTENANCE OF ROAD (WHISH IS DAMAGED FOR LAYING PIPELINE BY PHE DEPTT) NAMELY NARUGRAM H.C TO BADSHI ROAD VIDE- PACKAGE NO- WB 22 12 UNDER PMGSY-III UNDER NARUGRAM GP. & RAINA-I BLOCK, IN PURBA BARDHAMAN DISTRICT |  |  | BILL/00740/2024-2025 | 894/JJM | 25/09/2024 | 25/09/2024 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 3.86 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Laying of 150mm DI pipeline for interconnection of 4no tw to distribution line & Kalsi mouza 3rd tw to distribution line for Bagila Piped Water Supply Scheme under memari-I Block, District:- Purba-Bardhaman. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001071/2024-2025 | 105/BSD | 16/01/2025 | 15/02/2025 | A.R. TRADERS | 1.88 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08704 | Retrofitting | Construction of switch room cum chlorine room without toilet room at 4th Tube well site according to departmental drawing no.- PHE/BD/P.H/DRG-01/DCE-2017 for Bagila piped water supply scheme at Sanghatipally under Memari-I Block under Burdwan Sub-Division, PHE Dte within Burdwan Division PHE Dte. Dist- Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000043/2025-2026 | 1025/BSD | 08/05/2025 | 06/08/2025 | H SAMANTA | 4.16 | 0 | 0 | 100
Total | [13 empty] | 142.88 | 19.44 | 13.61