## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Gobindapur piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08706 | Retrofitting | Providing FHTC from dist. System within the command area of GOBINDAPUR Piped Water Supply Scheme at Gobindapur (Part), Ichabacha, Taherpur, Dangapara, Purba Kashiara (Part), Matdanga, Chilinda, Sitarampur Village at Memari-I Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000373/2021-2022 | 210/BWD | 11/01/2022 | 10/02/2022 | A R TRADERS | 28.37 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Gobindapur piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08706 | Retrofitting | Emergent 56 Nos. Street Stand Post closed for FHTC Work under Gobindapur Piped Water Supply Scheme (Retro Fittings) under Burdwan Sub-Divn.within Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000582/2022-2023 | 1974/BSD | 16/11/2022 | 01/12/2022 | A R TRADERS | 0.24 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Gobindapur piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | SM/08706 | Retrofitting | Beautification of PWSS with Land filling and arboriculture of Head Works site & 2nd pump house Gobindapur Pwss under memari-i Development Block under Burdwan Division, PHE Dte. |  | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000547/2024-2025 | 278/RWS | 03/09/2024 | 13/09/2024 | MUNSHI JAVEDUR JAMAN | 0.97 | 0 | 0 | 0
Total | [13 empty] | 29.58 | 0 | 0