## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Providing Functional Household Tap Connection from existing distribution system within the command area of JAGGESWARDIHI PWSS under Sitalgram village under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. | Assistant Engineer |  | ORD/000163/2022-2023 | 3150/BWD | 20/07/2022 | 19/08/2022 | BAMDEB CONSTRUCTION & CO | 15.4 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Extension of pipeline from the existing distribution system within scheme jurisdiction at Kanaidanga under Jaggeswardihi piped water supply scheme under Mongalkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-2] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000830/2020-2021 | 82/KTS | 09/02/2021 | 24/02/2021 | HAMID SK | 1.25 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Mongalkote Block under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000407/2021-2022 | 284/BWD | 17/01/2022 | 16/02/2022 | BABUL SK | 6.81 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jageswardihi Piped Water Supply Scheme at Kaichar & Sitalgram Village (Mouza), Mongolkot Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000258/2021-2022 | 6694/BWD | 01/12/2021 | 30/01/2022 | HAMID SK | 58.77 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Surging of existing tube well at 1st , 2nd and 3rd Tube Well Site at Jaggeswardihi under Jaggeswardihi Piped Water Supply Scheme under Mongalkote Block under Katwa Sub-Division within Burdwan Division, P.H.E.Dte [Sl No-02] | Assistant Engineer |  | ORD/000594/2021-2022 | 149/KTS | 23/02/2022 | 10/03/2022 | PARTHA PRATIM ACHARYA | 1.03 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Jaggeswardihi village under Jaggeswardihi PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.. [Sl No-03] | Assistant Engineer |  | ORD/000606/2021-2022 | 170/KTS | 25/02/2022 | 04/03/2022 | BABUL SK | 2.05 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of JAGGESWARDIHI and its adjoining mouzas Piped Water Supply Scheme, Block Mongalkote, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000535/2022-2023 | 4959/BWD | 09/11/2022 | 09/12/2022 | ANIRUDDHA FARUQUE | 13.08 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Extension of pipe line at Kaichar Paschim Para from the existing Distribution System within scheme jurisdiction under Jaggeswardihi PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-06] | Assistant Engineer |  | ORD/000609/2021-2022 | 173/KTS | 25/02/2022 | 12/03/2022 | BABUL SK | 4.67 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Extension of pipe line at Kaichar Khane Para from the existing Distribution System within scheme jurisdiction under Jaggeswardihi PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-04] | Assistant Engineer |  | ORD/000607/2021-2022 | 171/KTS | 25/02/2022 | 12/03/2022 | BABUL SK | 4.64 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Quotation from WBSEDCL for additional T/W at Jaggeswardihi w/s scheme under Burdwan Division, PHE Dte. |  |  | BILL/00895/2024-2025 | 1035/JJM | 25/10/2024 | 25/10/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Construction of Pump House, Boundary walls and Raising Main for Aug. of JAGGESWARDIHI Piped Water Supply Scheme under Mongalkote Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000922/2023-2024 | 5494/BWD | 13/12/2023 | 01/01/2025 | PAPRI HAZRA | 10.13 | 0 | 0 | 75
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Balance works for different type of works in connection with Jaggeswardihi PWSS, Deulia PWSS, Kunda PWSS and Gohagram PWSS Under Mongalkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001186/2024-2025 | 593/BWD | 07/02/2025 | 07/06/2025 | MD HASIN | 203.38 | 0 | 0 | 20
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08707 | Retrofitting | Providing FHTC (151 Nos.) of the left out house hold at Ichak habitation including Laying of pipe line from the existing Distribution System within the command area of JAGGESWARDIHI Piped Water Supply Scheme at Mangalkote Block under Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001121/2024-2025 | 495/BWD | 28/01/2025 | 27/02/2025 | ABDUL HAI | 8.3 | 0 | 0 | 0
Total | [13 empty] | 332.74 | 0 | 0