## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-A.Gr. D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000214/2021-2022 | 1476/BSD | 09/11/2021 | 09/12/2021 | MUNSHI JAVEDUR JAMAN | 4.83 | 4.83 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-B..Gr. E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000215/2021-2022 | 1477/BSD | 09/11/2021 | 09/12/2021 | DUBE ENTERPRISE | 4.83 | 4.8 | 99.28 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamarhati Z-II Piped Water Supply Scheme at Gotan, Kamarhati & Jashapur Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000235/2021-2022 | 6535/BWD | 24/11/2021 | 23/01/2022 | KOUSIK MALLICK | 71.1 | 66.22 | 93.14 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-A.Gr. D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000307/2021-2022 | 1686/BSD | 17/12/2021 | 16/01/2022 | MUNSHI JAVEDUR JAMAN | 4.83 | 4.83 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-B..Gr. E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000308/2021-2022 | 1685/BSD | 17/12/2021 | 16/01/2022 | DUBE ENTERPRISE | 4.83 | 4.83 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Kamarhati village within Raina-II Block , under Burdwan Division, PHE Dte. (Zone-II). Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000549/2021-2022 | 369/BSD | 02/03/2022 | 01/04/2022 | DUBE ENTERPRISE | 4.98 | 4.97 | 99.89 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Jashapur village within Raina-II Block , under Burdwan Division, PHE Dte.Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000465/2021-2022 | 276/BSD | 15/02/2022 | 17/03/2022 | KOUSIK MALLICK | 4.99 | 4.98 | 99.81 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Laying pipeline with FHTC for KAMARHATI Zone -II Water Supply Scheme at Kamarhati village (95 Nos.), Barati village (155 Nos.), Baidyapur village (110 Nos.), Jashapur village (125 Nos.) of Raina-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000164/2022-2023 | 3166/BWD | 21/07/2022 | 04/09/2022 | ANWESHA CONSTRUCTION | 31.48 | 31.37 | 99.64 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | FHTC for Kamarhati (Zone-II) Water Supply Scheme at Kamarhati Village (36 Nos) of Raina II Block under Burdwan Division, PHE Dte [For 100% FHTC at Kamarhati Village (Harghar Jal). Gr.J | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000342/2022-2023 | 1367/BSD | 04/08/2022 | 09/08/2022 | ANWESHA CONSTRUCTION | 0.98 | 0 | 0 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Barati and Badyapur village within Raina-II Block , under Burdwan Division, PHE Dte(Zone-II). Gr.D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000442/2021-2022 | 200/BSD | 01/02/2022 | 03/03/2022 | ARISTOCON ENGINEERS CO-OP SOCIETY LTD | 4.8 | 4.74 | 98.68 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | 225mm.Dia UPVC Pipeline at Node 11A to 11B of KAMARHATI(Zone-I)Water Supply Scheme within Raina-II Block , under Burdwan Division, PHE Dte. Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000387/2021-2022 | 58/BSD | 13/01/2022 | 12/02/2022 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 2.99 | 0 | 0 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | 225mm.Dia UPVC Pipeline at Node 86C-92,86-B-86C,86-A-86B,10-11-53-53A of KAMARHATI(Zone-I)Water Supply Scheme within Raina-II Block , under Burdwan Division, PHE Dte. Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000388/2021-2022 | 59/BSD | 13/01/2022 | 12/02/2022 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 3.96 | 3.92 | 99.06 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Formal Work Order for Laying distribution system including providing house connection at Nizampur, Daminya village (Mouza) of KAMARHATI Piped W/S. Scheme (Zone-I) at Raina - II Block under Burdwan Division, PHE. Dte.(Part-B) _2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000934/2020-2021 | 1601/BWD | 22/02/2021 | 23/05/2021 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 184.73 | 168.79 | 91.38 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Kamarhati village (Purba para,Pal para,Kana para,Pandit para, pashim para)within Raina-II Block, under Burdwan Division, PHE Dte. Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000031/2022-2023 | 678/BSD | 22/04/2022 | 22/05/2022 | BAMDEB CONSTRUCTION & CO | 2.84 | 2.83 | 99.68 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at GOTAN village within Raina II Block, under Burdwan Division, PHE Dte. Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000674/2021-2022 | 534/BSD | 28/03/2022 | 27/04/2022 | KOUSIK MALLICK | 4.96 | 4.96 | 99.89 | 1
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Bullah pilling (92.0 mtr) at HD Works Site(North,East & South) for protection of Boundary wall beside irrigation canel of KAMARHATI ZONE-II W/S Scheme of RAINA-II Block at Burdwan Sub -Division within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman.Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000644/2021-2022 | 468/BSD | 21/03/2022 | 05/04/2022 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.61 | 0 | 0 | 1
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Laying of interconnection of the Pump No.-1 & 2 with OHR and distribution main of 300 mm dia for Kamarhati (Zone-II) piped water supply scheme within Raina-II Block under Burdwan Division, PHE Dte.[Gr.-H] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000690/2021-2022 | 959/BSD | 23/07/2021 | 22/08/2021 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.8 | 0 | 0 | 1
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Pipeline with FHTC for KAMARHATI ZONE -II Water Supply Scheme at Kamarhati village(80 NOS) of Raina-II Block,under Burdwan Division, PHE Dte. Group : C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000111/2022-2023 | 1016/BSD | 20/06/2022 | 20/07/2022 | D.M. ENTERPRISE | 4.94 | 4.91 | 99.36 | 1
19 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Pipeline with FHTC for KAMARHATI ZONE -II Water Supply Scheme at Kamarhati village (52 Nos.) of Raina-II Block,under Burdwan Division, PHE Dte. Group : A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000113/2022-2023 | 1035/BSD | 20/06/2022 | 20/07/2022 | KOUSIK MALLICK | 4.96 | 4.8 | 96.89 | 1
20 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Pipeline with FHTC for KAMARHATI ZONE -II Water Supply Scheme at Kamarhati village(70 NOS) of Raina-II Block,under Burdwan Division, PHE Dte. Group : B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000110/2022-2023 | 1015/BSD | 20/06/2022 | 20/07/2022 | KONAR ENTERPRISE | 4.95 | 4.85 | 97.9 | 1
21 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | Land Development(at entrance)of Head Works Site of of KAMARHATI ZONE-II PIPED Water Supply Scheme at RAINA-II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. Group : F. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000108/2022-2023 | 988/BSD | 16/06/2022 | 01/07/2022 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 1.85 | 0 | 0 | 1
22 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | SM/08709 | Retrofitting | FHTC for KAMARHATI (Zone-II] Water Supply Scheme at Kamarhati village (36 Nos) of Raina-II Block under Burdwan Division, PHE Dte. [for 100% FHTC at Kamarhati village (Harghar Jal)] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000653/2022-2023 | 1367-A/BSD | 04/08/2022 | 09/08/2022 | ANWESHA CONSTRUCTION | 0.98 | 0.98 | 100 | 1
Total | [13 empty] | 364.23 | 327.61 | 89.95