## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | SM/08711 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for the balance household in (Kolsara, Kulingram Uttar, Kulingram Dakshin, Ranapara Uttar, Ranapara Dakshin, Dutta Para, Kantagoria, Gokul, Gopalpur, Reora & Chack) Part Habitations from existing distribution system within the command area of KULINGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000126/2021-2022 | 4536/BWD | 06/09/2021 | 06/10/2021 | SK ALIM | 31.2 | 30 | 96.17 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | SM/08711 | Retrofitting | Extension of pipeline for KULINGRAM Water Supply Scheme FOR FHTC work within Jamalpur Block , under Burdwan Division, PHE Dte. Gr.B | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000440/2021-2022 | 198/BSD | 01/02/2022 | 03/03/2022 | SK ALIM | 4.34 | 3.37 | 77.59 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | SM/08711 | Retrofitting | HDPE pipeline of 75 mm dia of Kulingram water supply scheme for FHTC (Gopalpur, Ranapara, Koisara, Gokul Katagoria)of Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000703/2021-2022 | 1424/BSD | 25/10/2021 | 24/11/2021 | SK ALIM | 4.52 | 4.48 | 99.12 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | SM/08711 | Retrofitting | Relaying of damage of pipeline due to irrigation cannel and 75 mm dia HDPE pipeline with FHTC for KULINGRAM Water Supply Scheme within Jamalpur Block,under Burdwan Division, PHE Dte. Group : A | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000088/2022-2023 | 828/BSD | 23/05/2022 | 22/06/2022 | BISWAKARMA CONSTRUCTION | 4.96 | 4.66 | 94.07 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | SM/08711 | Retrofitting | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for KULINGRAM Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000073/2022-2023 | 2473/BWD | 12/05/2022 | 11/06/2022 | NADIA TUBEWELLS | 10.32 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | SM/08711 | Retrofitting | Extension of pipeline for Kulingram Water Supply Scheme (Rewra village, Gokul Village, Kulingram uttar Village, Chak Village, Ranapara Village, Kantagaria Village, Mirjapur Village, Duttapara Village, Kolsara Village, Gopalpur Village) within Jamalpur Block including water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000007/2021-2022 | 3116/BWD | 02/06/2021 | 01/08/2021 | SK ALIM | 151.26 | 291.46 | 192.69 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | SM/08711 | Retrofitting | Laying of Interconnection of 4th Tube well site and Laying of 90 mm dia HDPE pipeline for KULINGRAM Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000622/2023-2024 | 3917/BWD | 05/09/2023 | 05/10/2023 | BARABELUN NO.-II G.P. UNEMPLOYED CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.28 | 6.08 | 73.42 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | SM/08711 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Gopalpur Village, Jamalpur Block within Kulingram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000796/2023-2024 | 875/AE/HQ | 07/11/2023 | 07/12/2023 | PAPRI HAZRA | 0.76 | 0.72 | 95.4 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | SM/08711 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Gangarambati Village, Jamalpur Block within Kulingram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000797/2023-2024 | 876/AE/HQ | 07/11/2023 | 07/12/2023 | PAPRI HAZRA | 0.76 | 0.72 | 95.4 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | SM/08711 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | AE(HQs),AE(HQs), Burdwan Division, PHE Dte. | Junior Engineer, Burdwan Division | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 20/05/2025 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
Total | [13 empty] | 349.02 | 341.49 | 97.84