## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. | SM/08713 | Retrofitting | Connection of CWR & IEP with the existing distribution system under Natungram Piped Water Supply Scheme under Katwa Sub-Division under Burdwan Division, P.H.E. Dte. [Sl No-01] | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000596/2021-2022 | 160/KTS | 24/02/2022 | 26/03/2022 | JAHAR GHOSH | 1.5 | 1.36 | 90.26 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. | SM/08713 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Natungram Piped Water Supply Scheme at Natungram (Part) & Charnarayanpur Village (Mouza), Ketugram-II Block under Burdwan Division, PHE Dte. (Agreement no. 567/BWD of 2020-2021) | AE(HQs) | J.E. 2 BURDWAN | ORD/000294/2020-2021 | 357/BWD | 15/01/2021 | 14/02/2021 | JAHAR GHOSH | 22.73 | 6.83 | 30.04 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. | SM/08713 | Retrofitting | Construction of sanitary system and drinking water supply arrangement for Head Work Site of Natungram Water Supply Scheme under Katwa Sub-Division within Burdwan Division P.H.E Dte. (Sl No-3) | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000275/2021-2022 | 800/KTS | 10/12/2021 | 24/01/2022 | JAHAR GHOSH | 1 | 0.23 | 23.04 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. | SM/08713 | Retrofitting | Construction of Boundary wall including land development, Pathway and plantation at Head works site of Natungram water supply scheme, Block-Ketugram-II under Katwa Sub-Division under Burdwan Division, PHE Dte. [Tr No.-347/BWD/20-21] | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000482/2020-2021 | 4282/BWD | 03/11/2020 | 02/01/2021 | MOJAI SK | 31.33 | 8.94 | 28.54 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. | SM/08713 | Retrofitting | Regarding release of fund for restoration of road under PMGSY scheme under Ketugram-II Block Katwa Sub-Division PHE Dte. Khatundi to Chitahati (Package No-WB-22-47) |  |  | BILL/00772/2024-2025 | 896/JJM | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 2.45 | 0 | 0 | 0
Total | [13 empty] | 59.02 | 17.36 | 29.41