## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Additional extension UPVC distribution Pipeline in connection with FHTC work for Palsit Piped Water Supply Scheme at Khargram, Karanda, Palsit & Bhaita under Bardhaman- II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000172/2021-2022 | 6065/BWD | 07/10/2021 | 06/11/2021 | BRINDABAN KONAR | 14.22 | 13.89 | 97.69 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H/3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of July & August'2022. |  |  | VCH/000645/2022-2023 | 612/VEH/22-23 | 23/09/2022 | 23/09/2022 | MD HASIN | 0.56 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Construction of boundary wall including land development at 2nd Pump house of PALSIT within command area of PALSIT Piped W/S. Scheme under Burdwan Division, PHE. Dte. [Group : F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000057/2022-2023 | 238/AE/HQ | 19/04/2022 | 19/05/2022 | M/S F.S. ENTERPRISE | 0.96 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of PALSIT & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000523/2022-2023 | 4886/BWD | 02/11/2022 | 02/12/2022 | WESTERN WATER SUPPLY AGENCY | 10.04 | 10.04 | 100 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Providing FHTC for 100% coverage in different village from existing distribution system within PALSIT PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000790/2022-2023 | 1423/BWD | 24/03/2023 | 23/04/2023 | BABUL SK | 28.53 | 27.27 | 95.59 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Palsit piped water supply scheme at Bhaita (11 Nos Habitation), Khargram (17 Nos. Habitation), Palsit (19 Nos. Habitation), Karanda (17 Nos. Habitation) & Paschim Chandipur village, Bardhaman-II Block under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000528/2020-2021 | 5000/BWD | 10/12/2020 | 10/03/2021 | BRINDABAN KONAR | 96.95 | 55.82 | 57.58 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for PALSIT its Adjoining Mouza W/S Scheme, Block -Bardhaman-II within Burdwan Sub-Division, PHE Dte. (Mouza- KARANA) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000766/2022-2023 | 498/BSD | 21/03/2023 | 05/05/2023 | M/S PALASH BISWAS | 3.32 | 3.17 | 95.63 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Providing parallel distribution system from Khargram more to Bhaita High School within PALSIT PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000968/2023-2024 | 005/BWD | 02/01/2024 | 01/02/2024 | TARAMA AGENCY | 20.68 | 18.8 | 90.9 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Providing left out FHTC for 100% coverage in different village within PALSIT PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000153/2024-2025 | 1038/BSD | 10/06/2024 | 10/07/2024 | M/S PALASH BISWAS | 0.95 | 0.94 | 99.21 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Providing left out FHTC for 100% covarage in different village within PALSIT PWSS , Bardhhaman-II Development Block under Burdwan Division, PHE Dte. |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000116/2024-2025 | 995/BSD | 06/06/2024 | 06/07/2024 | M/S PALASH BISWAS | 0.96 | 0.95 | 99.6 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Laying of inter connection R.main to OHR,OHR to LDS & By pass connection for PALSIT PWSS under Burdwan Sub-Division under Burdwan Division,PHE Dte. |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001280/2024-2025 | 503/BSD | 06/03/2025 | 11/04/2025 | HAMID SK | 0.94 | 0 | 0 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | SM/08714 | Retrofitting | Designing,making and erection of Sign Board for SWAJAL GRAM in Paschim Chandipur village of Burdwan-II Block under Palsit Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos. Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000470/2025-2026 | 2336/BSD | 21/08/2025 | 31/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
Total | [13 empty] | 178.83 | 130.89 | 73.19