## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Srikhanda mouza within the command area of Srikhanda piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08716 | Retrofitting | Supplying, laying and commissioning of Rising main at pump no. - 2 of Srikhanda PWSS under Katwa Sub-Division under Burdwan Division, PHE Dte. [Sl No-07] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000161/2022-2023 | 444/KTS | 27/06/2022 | 27/07/2022 | ASHOK KUMAR GHOSH | 1.84 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Srikhanda mouza within the command area of Srikhanda piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08716 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of SRIKHANDA and its adjoining mouzas Piped Water Supply Scheme, Block Katwa I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000669/2022-2023 | 388/BWD | 31/01/2023 | 02/03/2023 | SUBODH KUMAR MONDAL | 11.81 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Srikhanda mouza within the command area of Srikhanda piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08716 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SRIKHANDA Piped Water Supply Scheme at Katwa - I Block under Burdwan Division, PHE Dte.(Agreement No. 53/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer |  | ORD/000121/2020-2021 | 4880/BWD | 07/12/2020 | 07/03/2021 | ASHOK KUMAR GHOSH | 96.84 | 0 | 0 | 1
Total | [13 empty] | 110.49 | 0 | 0