## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Survey and Collection of data through mobile application regarding availability of drinking water, sanitation facilities and other parameters in Primary & Upper Primary Schools, Anganwadi Centers under Katwa -I , Katwa- II , Ketugram-I, Ketugram-II and Mongalkote Block within Purba Bardhaman District under Katwa Sub-Division under Burdwan Division, PHE Dte (Sl No-1) | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000968/2020-2021 | 314/A/KTS | 09/11/2020 | 17/02/2021 | GHOSH CONSTRUCTION | 2.47 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Survey and collection of data through mobile application regarding availability of drinking water, sanitation, facilities and other parameters in Primary & Upper Primary schools, Anganwari Centres under Burdwan-I, Burdwan-II, Raina-II, Memari-I, Memari-II, Jamalpur & Khandaghosh Block within Purba Bardhaman District under Burdwan Division, PHE Dte. |  |  | ORD/000983/2020-2021 | 1031/BSD | 13/11/2020 | 13/02/2021 | ALAKA GHOSH | 3.27 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Survey and collection of data through mobile application regarding availability of drinking water, sanitation facilities and other parameters in Primary & Upper Primary schools, Anganwari Centres under Kalna-I, Kalna-II, Purbasthali-I, Purbasthali-II and Monteswar Block within Purba Bardhaman District under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001338/2020-2021 | 767/KSD | 27/11/2020 | 07/03/2021 | SETH ENTERPRISE | 1.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Samaspur Village, Monteswar Block within Lohana PWSS under Burdwan Division, PHE Dte. (5 Nos Board) |  | J.E. 1 BURDWAN | ORD/001076/2023-2024 | 829/AE/HQ | 30/10/2023 | 29/11/2023 | ISHAN CONSTRUCTION | 0.76 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Takipur Village, Ausgram-I Block within Takipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) |  | J.E. 1 BURDWAN | ORD/001077/2023-2024 | 824/AE/HQ | 30/10/2023 | 29/11/2023 | ISHAN CONSTRUCTION | 0.76 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Chonari Village, Ausgram-I Block within Takipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) |  | J.E. 1 BURDWAN | ORD/001078/2023-2024 | 822/AE/HQ | 30/10/2023 | 29/11/2023 | ISHAN CONSTRUCTION | 0.76 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Jarul Village, Khandaghosh Block within Taraposh PWSS under Burdwan Division, PHE Dte. (5 Nos Board) |  | J.E. 1 BURDWAN | ORD/001112/2023-2024 | 868/AE/HQ | 07/11/2023 | 07/12/2023 | PAPRI HAZRA | 0.76 | 0 | 0 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Chalbalpur Village, Jamalpur Block within Chak Sanjadi PWSS under Burdwan Division, PHE Dte. (5 Nos Board) |  | J.E. 1 BURDWAN | ORD/001113/2023-2024 | 874/AE/HQ | 07/11/2023 | 07/12/2023 | PAPRI HAZRA | 0.76 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Paschim Memari Village, Memari - I Block within Nabagram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/001197/2023-2024 | 865/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 0 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Pingur Village, Memari - I Block within Nabagram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/001198/2023-2024 | 864/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Supply, fitting & fixing of Har Ghar Jal Logo and Wall painting of Scheme detailing of Nabagram & Kulingram Piped W/S. Scheme under Jamalpur Block under Burdwan Division, PHE. Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/001200/2023-2024 | 912/AE/HQ | 29/11/2023 | 09/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 1 | 0 | 0 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. | SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Konarpara Village, Memari - I Block within Nabagram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/001199/2023-2024 | 858/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 0 | 100
Total | [13 empty] | 14.23 | 0 | 0