## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | SM/08998 | Augmentation | Route Survey & Preparation of DPR for Parhati W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.13. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000502/2021-2022 | 188/BSD | 31/01/2022 | 02/03/2022 | RADIANT | 2.72 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | SM/08998 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | SM/08998 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000519/2022-2023 | 4703/BWD | 19/10/2022 | 08/11/2022 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | SM/08998 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PARHATI Piped Water Supply Scheme (Mouza- Akalia, Chandipur, Ganti, Kabastigiri, Kanpur, Kasipur, Madhupur, Parhati, Tajpur) of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000551/2022-2023 | 5193/BWD | 24/11/2022 | 08/01/2023 | ANWESHA CONSTRUCTION | 39.72 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | SM/08998 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2021-2022 | 904/BWD | 15/02/2022 | 15/02/2022 | Resource Division | 11.38 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | SM/08998 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2021-2022 | 549/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 16.9 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | SM/08998 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000198/2021-2022 | 1521/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | SM/08998 | Augmentation | Providing Balance Functional Household Tap Connection (848 nos FHTC) from existing distribution system within the command area of PARHATI Piped Water Supply Scheme at (Akalia, Chandipur, Ganti, Kabastigiri, Kanpur, Kasipur, Madhupur, Parhati, Tajpur) Mouza, Construction of boundary wall at head work site & 2nd T/W site under MEMARI-II Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000776/2022-2023 | 1363/BWD | 22/03/2023 | 21/05/2023 | ASHOK KUMAR GHOSH | 53.71 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | SM/08998 | Augmentation | Augmentation of PARHATI Piped Water Supply Scheme with LDS, Construction of 350 Cum capacity OHR with 20.0 Mtgr. Staging height inclusive of soil test & FHTC under Memari - II Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000597/2021-2022 | 1472/BWD | 14/03/2022 | 14/03/2023 | ASHOK KUMAR GHOSH | 361.27 | 0 | 0 | 100
Total | [13 empty] | 3505.52 | 0 | 0