## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Rejuvenation of Bhalki Water Supply Scheme. | SM/09103 | Augmentation | Restoration of Pipeline by Re-Laying of Pipe Line for Rejuvenation of BHALKI and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000104/2021-2022 | 3877/BWD | 27/07/2021 | 25/09/2021 | ASHOK KUMAR GHOSH | 279.81 | 276.39 | 98.78 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Rejuvenation of Bhalki Water Supply Scheme. | SM/09103 | Augmentation | Construction of Drain and restoration of connection for Augmentation of BHALKI W/S Scheme , Block- Ausgram-II, under Durgapur (Burdwan North)Sub Division Burdwan Division, P.H.E. Dte. [SL-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000121/2022-2023 | 334/DSD | 27/06/2022 | 27/07/2022 | TAUSIF HOSSAIN MONDAL | 1.88 | 1.87 | 99.36 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Rejuvenation of Bhalki Water Supply Scheme. | SM/09103 | Augmentation | Making structure with GI pipe for provision of joining and laying of pipeline near Abhirampur branch Canal for Bhalki and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-H] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000134/2022-2023 | 349/DSD | 30/06/2022 | 14/08/2022 | PARTHA RAY | 1.9 | 1.82 | 96.06 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Rejuvenation of Bhalki Water Supply Scheme. | SM/09103 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of augmentation BHALKI Piped Water Supply Scheme at Bhalki (Part), Chandipur (Part), Samantapara (Part), Telota (Part) & Abhirampuri (Part) village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000006/2022-2023 | 1907/BWD | 07/04/2022 | 07/05/2022 | ROY CONSTRUCTION | 49.52 | 0 | 0 | 1
Total | [13 empty] | 333.11 | 280.08 | 84.08