## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-C) [SL. No. : 11] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000031/2021-2022 | 3408/BWD | 25/06/2021 | 10/07/2021 | N.S. ENTERPRISE | 4.86 | 0.59 | 12.14 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Jougram village of Jougram piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte..Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000311/2021-2022 | 1033/BSD | 05/08/2021 | 04/09/2021 | N.S. ENTERPRISE | 0.69 | 0.67 | 96.8 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jaugram Piped Water Supply Scheme at Jaugram Village (P) (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000278/2021-2022 | 6952/BWD | 14/12/2021 | 13/01/2022 | SAIKAT RAY | 33.69 | 29.78 | 88.4 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Land Development at Jougram 4th T/W Site at Jamalpur Block under Burdwan Sub Division in Burdwan Division,PHE Dte. Gr.G. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000445/2022-2023 | 1487/BSD | 26/08/2022 | 25/09/2022 | PANCHANAN CHAKROBORTY | 1.17 | 1.1 | 94.15 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Replace damaged and chokaged various dia. A.C. Pipeline with UPVC pipes, construction of valve chambers and providing FHTC at mouza (Habitation) under JOUGRAM PWSS, Jamalpur Development Block of Burdwan Sub-Division under Burdwan Division, PHE Dte". Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000475/2022-2023 | 1599/BSD | 14/09/2022 | 14/10/2022 | MUKHERJEE ENTERPRISE | 3.38 | 3.19 | 94.34 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Laying of 100 mm dia D.I Pipe for Road widening from 4 lane to 6 lane of NH2 at chainage 599+654 & 599+154 at Jougram Water supply within Jamalpur Block,under Burdwan Division,PHE Dte". Group : B. |  |  | ORD/000109/2022-2023 | 981/BSD | 16/06/2022 | 16/07/2022 | PRATIVA CONSTRUCTION | 2.97 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Concrete road at Head Work site Tubewell site of Jaugram Water Supply Scheme under JAMALPUR Block of Burdwan Division, PHE Dte. Gr.L | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000484/2022-2023 | 1608/BSD | 14/09/2022 | 29/09/2022 | DUBE ENTERPRISE | 1.7 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ilsora village and Ilsora habitation of JAUGRAM Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6A¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000779/2020-2021 | 3330/BWD | 18/09/2020 | 18/10/2020 | MUKHERJEE ENTERPRISE | 4.86 | 4.86 | 100 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Replacement of 775 meter AC pipeline by using UPVC pipeline in Jaugram piped water supply scheme at Jamalpur Block under Burdwan Division PHE Dte.Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000400/2021-2022 | 69/BSD | 14/01/2022 | 13/02/2022 | MUKHERJEE ENTERPRISE | 4.83 | 4.71 | 97.62 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE/RWS/JAMALPUR | ORD/000345/2021-2022 | 40/BWD | 05/01/2022 | 04/02/2022 | PREMANANDA ROY BISWAS | 22.68 | 3.33 | 14.69 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Construction of Boundary wall at 4th Tubewell site Of Jaugram Water Supply scheme under JAMALPUR Block of Burdwan Division, PHE Dte. (LENGTH- 71.0M, COL.- 28 NOS )Gr.F. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000650/2021-2022 | 471/BSD | 21/03/2022 | 05/05/2022 | PANCHANAN CHAKROBORTY | 3.77 | 3.72 | 98.51 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE/RWS/JAMALPUR | ORD/000592/2021-2022 | 1454/BWD | 11/03/2022 | 10/04/2022 | PREMANANDA ROY BISWAS | 18.83 | 0 | 0 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Construction of Boundary wall at 3RD Tubewell site Of Jaugram Water Supply scheme under JAMALPUR Block of Burdwan Division, PHE Dte. (LENGTH- 70.0M , COL- 28 NOS ) Gr.E | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000649/2021-2022 | 470/BSD | 21/03/2022 | 05/05/2022 | MUKHERJEE ENTERPRISE | 3.83 | 3.81 | 99.6 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | BALANCE PORTION Boundary wall at 3RD Tubewell site Of Jaugram Water Supply scheme under JAMALPUR Block of Burdwan Division, PHE Dte. (LENGTH- 34.0M , COL- 14 NOS) GROUP : G | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000086/2022-2023 | 820/BSD | 20/05/2022 | 04/07/2022 | MUKHERJEE ENTERPRISE | 3.3 | 3.29 | 99.57 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Repairing and Restoration of damaged and chokaged various Dia UPVC Pipeline and Construction of Valve Chambers to conrrol flow of waer for providing FHTC in JOUGRAM PWSS at Jamalpur Dev.block under Burdwan Division,PHE Dte.Group : D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000112/2022-2023 | 1017/BSD | 20/06/2022 | 20/07/2022 | MUKHERJEE ENTERPRISE | 1.43 | 1.39 | 96.6 | 1
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Providing FHTC for Dogachia Mouza [(Habitation (Village)] for AMRA piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000068/2023-2024 | 2019/BWD | 28/04/2023 | 28/05/2023 | DEY NIRMAN | 20.61 | 2.37 | 11.52 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ilsora village and Ilsora habitation of JAUGRAM Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6A¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001347/2020-2021 | 4513/BWD | 12/11/2020 | 12/12/2020 | MUKHERJEE ENTERPRISE | 4.86 | 1.98 | 40.71 | 100
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Moyna Habitation of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [GROUP - 'B'] |  |  | ORD/001346/2020-2021 | 2401/BWD | 20/07/2020 | 19/08/2020 | DEY NIRMAN | 4.92 | 4.05 | 82.35 | 100
19 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B) [SL. No. : 13] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000444/2020-2021 | 1398/BWD | 15/02/2021 | 02/03/2021 | DEY NIRMAN | 4.84 | 4.84 | 100 | 0
20 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | SM/09104 | Retrofitting | Laying of pipeline for providing FHTC 100% coverage and also construction & installation of Sluice Valve & Valve Chamber to control the flow of water, road restoration work etc. of different Piped W/S Schemes, Block Jamalpur under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000194/2024-2025 | 2488/BWD | 01/07/2024 | 02/01/2026 | M/S NATIONAL CONSTRUCTION | 480.97 | 0 | 0 | 80
Total | [13 empty] | 628.18 | 73.68 | 11.73