## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Preparation of DPR for augmentation of Anukhal W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-D) | Assistant Engineer |  | ORD/000570/2021-2022 | 206/KSD | 23/02/2022 | 16/03/2022 | INDRANIL DUTTA & ASSOCIATES | 2.86 | 2.82 | 98.54 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000210/2021-2022 | 1533/BWD | 15/03/2022 |  | Resource Division | 0.37 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2021-2022 | 1204/BWD | 04/03/2022 |  | Resource Division | 22.68 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2021-2022 | 531/BWD | 27/01/2022 |  | Resource Division | 14.56 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2021-2022 | 1242/BWD | 07/03/2022 |  | Resource Division | 4.93 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000160/2021-2022 | 1320/BWD | 08/03/2022 |  | Resource Division | 32.89 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 4627/BWD | 17/10/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Work Order for Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory under The Assistant Engineer, Kalna Sub-Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation,Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL : Anukhal Sub District Water Testing Laboratory under Kalna Sub Division.) | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000672/2023-2024 | 1335/KSD | 28/08/2023 | 27/09/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.91 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Augmentation of ANUKHAL Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation with construction of boundary wall at Headworks site under Kalna-II Block, District:- Purba-Burdwan. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000096/2022-2023 | 2741/BWD | 08/06/2022 | 08/06/2023 | SINGHA ROY AND CO. | 374.09 | 318.48 | 85.14 | 70
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Sinking of tube well, Laying dist. system, Providing FHTC, construction of Pump House & Boundary and Laying rising main of ANUKHAL Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000857/2023-2024 | 5206/BWD | 29/11/2023 | 28/03/2024 | SINGHA ROY AND CO. | 119.49 | 9.66 | 8.09 | 15
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | SM/09403 | Augmentation | Additional work to implement augmentation of ANUKHAL Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000821/2023-2024 | 4998/BWD | 21/11/2023 | 21/12/2023 | UDYOG CONSTRUCTION | 7.48 | 3.91 | 52.3 | 100
Total | [13 empty] | 3597.57 | 334.88 | 9.31